[image: image1.emf]

Healt Financing TWG  UPDATE  May, 2017
Last HFTWG met May 16th  
Health Financing Strategy, SNHI Bill, ICHF:

· Launch of ICHF action plan has been delayed due to difficulties between PORALG and MOHCDGEC to reach consensus on how to phase in the roll out of ICHF and the connected resource requirements.  PORALG, at the time of the TWG was still in disagreement of starting in 50 selected regions, in their opinion the roll out should immediately start throughout at whole country.  Currently 17 regions are partner supported and could benefit from DP support.  9 regions are unsupported and would thus suffer certain constraints.  
RBF
· Implementation currently ongoing in 5 regions (Shynianga, Mwanza, Singida, Pwani, ?).  Low facility enrolment in Mwanza and Singida due to large amount of facilities 0-star rated (need to be lifted to at least 1 star).  The RBF unit did not present financial up-dates relating to the roll out and was requested to prepare this was next meeting.
DFF

· PORALG send request for financial support to DPs to help finance the DFF related Facility Financial Accounting and Reporting System (FFARS) Training of Trainers and Facility staff in their focal regions.  This request is still being evaluated by the individual DPs.  PS3 is financing the training for 13 regions and has provided the cost per remaining regions to DPs. 
Other

· The HF TWG Chair recognized importance to pick up the topic of aligning HF with PFM for successful implementation of health financing reforms.  A joint meeting between the TWG HF and PFM will be called to discuss this subject and identify and divide tasks among the two groups.

· The ADP expressed interest in the development of a comprehensive Resources Tracking Tool – a more concrete concept note regarding this idea will be discussed at the next meeting.

Next HF TWG tentatively Tuesday 13th June 2017
[image: image2.png]Agenda 2012

—_—



Page 1 of 1

[image: image2.png]