**Natural Resources Annual Sector Review 2014**

**Summary of Priority Actions 2014-2015**

|  |
| --- |
| **Sub-Sector: Wildlife** |
|  | **Priority Action**  | **Indicator** | **Timing**  |
|  | To launch national anti-poaching strategy by November 2014 and to have started funding and implementation by June 2015 | More than 50% of) short term objectives/actions have been implemented  | by June 2015 |
|  | To launch the Tanzania Wildlife Management Authority (TAWA) | TAWA operationalized and functioning  | by June 2015 |
|  | To Strengthening local governance institutions (new) | 1. WMA regulations have been reviewed and non-consumptive regulations have been finalized. (Posting total revenues and distribution to all WMAs),  | By October 2015  |
| 2. Number of functioning WMAs |  |
|  | To creating a conducive environment for tourism growth/business/investment. | 1. a plan is in place to address business enabling environment issues  |  |
| 2. Representatives of private sector/tourism (representatives of the associations) on the board of TAWA and TANAPA, NDC Antiquities etc.  |  |
| 3. Identify what the aspects are that create the non-conducive environment. – TCT has already identified issues. Review of the act on PPP. Come up with an action plan based on the issues. |  |

|  |
| --- |
| **Sub-Sector: Forestry and Beekeeping** |
|  | **Priority Action**  | **Indicator** | **Who** | **How**  | **When**  |
| 1.  | Reduction of wood deficit by establishment of plantation forest and promotion of smallholders- driven tree growing initiatives | Number of plantation forest areas established  | Central, local govt, and private sectors and communities  | ReportingField visitReview meeting | Quarterly, semi and annually  |
| Area of woodlots under tree growers increased  | PFP, FBDand SHIVIMITA, TGA and communities, DP | ReportingField visitReview meeting | Quarterly, semi and annually |
| 2.  | Enhancing research and database for beekeeping  | Data on beekeeping potential collected and made available to the public | PFP, FBD and SHIVIMITA, TGA and communities, DP | ReportingField visitReview meeting | Quarterly, semi and annually |
| 3. | Value addition and utilization of the forest products | Number of new and efficient production technology unit introduced  | TFS, MNRT, SHIVIMITA,FDB | ReportingField visitReview meeting | Quarterly, semi and annually |

|  |
| --- |
| **Sub-Sector: Fisheries** |
|  | **Priority Action** | **Indicators**  | Timing:  |
| **1.** | Curb dynamite fishing | 1. Initiate baseline monitoring of blasts
2. Open > 10 new court cases
3. Establish & maintain database tracking court cases at FDD
4. Inter-ministry task force on dynamite fishing has produced strategy integrating inputs and plans from SWIOFish& SMARTFISH
 |  By 30 June 2015 |
| **2.** | Strengthen fisheries co-management (BMUs) | 1. Establish at FDD a BMU performance monitoring database with >100 BMUs
2. At least 10 more BMUs registered
 |  By 30 June 2015 |
| **3.** | Improve sector financing | 1. Prepare economic case to Min. of Finance for increase revenue allocation to MLFD for fisheries sector
 |  By 30 June 2015 |

|  |
| --- |
| **Sub-Sector: Tourism** |
|  | **Priority Action**  | **Indicator** |  |
|  | Review of the 1999 National Tourism Policy | Hurdles for tourism business reducedConducive business environment for tourism in place |  |
|  | Elaborate a domestic tourism marketing strategy and implement a domestic awareness campaign  | Share of domestic tourism increasedOverdependence on international tourism reduced |  |
|  | Grading/ Classification of accommodation facilities  |  |  |

|  |
| --- |
| **Sub-Sector: Antiquities**  |
|  | **Priority Action**  | **Indicator** |  |
|  | Review of the 1964 Antiquities Act  | Revised Antiquities Act in place  |  |
|  | Development of five selected sites: Mbozi Meteorite, Olduvai Gorge, Caravan Serai , Kwihara and Amboni Caves |  |  |
|  | Promotion campaign of all sites | Five TV programs airedCultural heritage resources exhibitions installed in two Tanzania’s Embassies abroad |  |