**Natural Resources Annual Sector Review 2014**

**Summary of Priority Actions 2014-2015**

|  |  |  |  |
| --- | --- | --- | --- |
| **Sub-Sector: Wildlife** | | | |
|  | **Priority Action** | **Indicator** | **Timing** |
|  | To launch national anti-poaching strategy by November 2014 and to have started funding and implementation by June 2015 | More than 50% of) short term objectives/actions have been implemented | by June 2015 |
|  | To launch the Tanzania Wildlife Management Authority (TAWA) | TAWA operationalized and functioning | by June 2015 |
|  | To Strengthening local governance institutions (new) | 1. WMA regulations have been reviewed and non-consumptive regulations have been finalized. (Posting total revenues and distribution to all WMAs), | By October 2015 |
| 2. Number of functioning WMAs |  |
|  | To creating a conducive environment for tourism growth/business/investment. | 1. a plan is in place to address business enabling environment issues |  |
| 2. Representatives of private sector/tourism (representatives of the associations) on the board of TAWA and TANAPA, NDC Antiquities etc. |  |
| 3. Identify what the aspects are that create the non-conducive environment. – TCT has already identified issues. Review of the act on PPP. Come up with an action plan based on the issues. |  |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Sub-Sector: Forestry and Beekeeping** | | | | | |
|  | **Priority Action** | **Indicator** | **Who** | **How** | **When** |
| 1. | Reduction of wood deficit by establishment of plantation forest and promotion of smallholders- driven tree growing initiatives | Number of plantation forest areas established | Central, local govt, and private sectors and communities | Reporting  Field visit  Review meeting | Quarterly, semi and annually |
| Area of woodlots under tree growers increased | PFP, FBDand SHIVIMITA, TGA and communities, DP | Reporting  Field visit  Review meeting | Quarterly, semi and annually |
| 2. | Enhancing research and database for beekeeping | Data on beekeeping potential collected and made available to the public | PFP, FBD and SHIVIMITA, TGA and communities, DP | Reporting  Field visit  Review meeting | Quarterly, semi and annually |
| 3. | Value addition and utilization of the forest products | Number of new and efficient production technology unit introduced | TFS, MNRT, SHIVIMITA,  FDB | Reporting  Field visit  Review meeting | Quarterly, semi and annually |

|  |  |  |  |
| --- | --- | --- | --- |
| **Sub-Sector: Fisheries** | | | |
|  | **Priority Action** | **Indicators** | Timing: |
| **1.** | Curb dynamite fishing | 1. Initiate baseline monitoring of blasts 2. Open > 10 new court cases 3. Establish & maintain database tracking court cases at FDD 4. Inter-ministry task force on dynamite fishing has produced strategy integrating inputs and plans from SWIOFish& SMARTFISH | By 30 June 2015 |
| **2.** | Strengthen fisheries co-management (BMUs) | 1. Establish at FDD a BMU performance monitoring database with >100 BMUs 2. At least 10 more BMUs registered | By 30 June 2015 |
| **3.** | Improve sector financing | 1. Prepare economic case to Min. of Finance for increase revenue allocation to MLFD for fisheries sector | By 30 June 2015 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Sub-Sector: Tourism** | | | |
|  | **Priority Action** | **Indicator** |  |
|  | Review of the 1999 National Tourism Policy | Hurdles for tourism business reduced  Conducive business environment for tourism in place |  |
|  | Elaborate a domestic tourism marketing strategy and implement a domestic awareness campaign | Share of domestic tourism increased  Overdependence on international tourism reduced |  |
|  | Grading/ Classification of accommodation facilities |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Sub-Sector: Antiquities** | | | |
|  | **Priority Action** | **Indicator** |  |
|  | Review of the 1964 Antiquities Act | Revised Antiquities Act in place |  |
|  | Development of five selected sites: Mbozi Meteorite, Olduvai Gorge, Caravan Serai , Kwihara and Amboni Caves |  |  |
|  | Promotion campaign of all sites | Five TV programs aired  Cultural heritage resources exhibitions installed in two Tanzania’s Embassies abroad |  |