## Slide 1: PROGRESS ON BRN IMPLEMENTATION OF STAR RATING OF PRIMARY HEALTH FACILITIES
Dr. Talhiya Yahya
Co-ordinator BRN star rating assessment of PHC-Facilities
HSIQAS-MOHSW
4/2/2015

## Slide 2: Background to BRN:
Solutions
to address the identified issues
Specific Facility Strengthening Approach
General Facility Strengthening Approach
Sol A
Sol B
issues
Imp A
Imp B
Solution A
Solution B
solutions that are independent on the assessment of health facilities and can be quickly implemented
Enablers
Development of baseline criteria and assessment tool to rate all primary level health facilities
While assessing and rating the selected health facilities, specific gaps are identified and will be addressed accordingly

## Slide 3: Background to BRN: specific strengthening of health facilities
Sol A
Sol B
issues
Imp A
Imp B
Assess and rate health facilities
Develop specific intervention program
Implement intervention program
Re-assess and rate health facilities
Iteration process
To address the on-the-ground issues, the lab will develop a criteria specific to the issues and then devise a rating mechanism to assess the health facilities
The assessment will be done to all Public, FBOs and Private primary level health facilities by FY2014/2015
Identify the conditions of the health facilities/service delivery, then develop specific intervention programmes
Description
Lab / BRN focus
Roll-out of specific strengthening programme
Re-assess health facilities to identify health facilities that have achieved 3 Stars and above
Repeat the process of developing specific intervention programmes for health facilties rated below level 3
Devise specific intervention plan for *12 mainland regions
Develop criteria for the assessment tool
Rate the health facilities using the developed assessment tool
Specific strengthening of health facilities will be focused on *12 mainland regions only, based on the developed intervention plan
80% of primary health facilities in the 12 regions will achieve 3 Stars and above
Provide rewards for health facilities that elevates into 3 Stars and above, while impose consequences for health facilities that do worse
Source(s): BRN Healthcare (2014)
* Regions may change after results of the nationwide assessment

## Slide 4: Background to BRN: Implementation of the intervention programs will be for *12 regions only
Sol A
Sol B
issues
Imp A
Imp B
Source(s): BRN Healthcare (2014)
Mara
Kilimanjaro
Arusha
Tanga
Lindi
Mtwara
Ruvuma
Iringa
Morogoro
Pwani
Dar Es Salaam
Dodoma
Singida
Rukwa
Mbeya
Kigoma
Tabora
Shinyanga
Kagera
Mwanza
Simiyu
Geita
Manyara
Katavi
Njombe
Assessment and rating of health facilities
Specific strengthening programmes
Number of regions:
25 (all mainland regions)
Number of health facilities = 6760
5824 dispensaries
716 health centres
220 district hospitals
Number of regions:
*12 (regions covered by HRH Distribution, Health Commodities & MNCH work streams)
Number of health facilities = 3023
2605 dispensaries
319 health centres
99 district hospitals
* Regions may change after results of the nationwide assessment

## Slide 5: Background to BRN: Leverage on the national and regional team to assess 6760 facilities by March 2015
National Team (HSIQAS)
160 people
Each member of National Team is assign to one council as facilitator for star rating
MoHSW (DCS, DPS, DHR)
Muhimbili National Hospital
National Institute for Medical Research
Medial Store Department
Tanzania Food and Drug Authority
RHMT and CHMT members to accompany assessors
  Total number of Hospitals at district level, Health Centers & Dispensaries
6760
1104
Council Team
  Estimated assessment duration
~ 4 weeks
1 HF /Day / team (2)
issues
sol.
Imp A
Imp B
6 assessors/LGA
(assessors to jointly assess district hospitals)
  Total number of assessors
2 assessors/disp & HCs
Team A
Team B
Team C
2 assessors/disp & HCs
2 assessors/disp & HCs
  Estimated assessment duration
~ 4 weeks
1 HF / 3Days / team (6)

## Slide 6: Background to BRN: Ensuring sustainability of the Star Rating by monetary and non-monetary rewards
Monetary:
  Less funds through RBF and NHIF
Non-monetary:
  Receives targeted technical support to improve
  Community aware of rating, performance decline, and monetary decrease through public posting
Monetary:
  More funds through RBF and NHIF
Non-monetary:
  Visible placing of stars, trends, and monetary amount in community.
  Greater decentralised devolution to facilities to manage increasing amounts and complex transactions, and hire staff
Assessment of facility
Specific Strengthening Activities
New STAR Rating!
More Stars 
Fewer Stars 
Specific implementation Plan
Sol A
Sol B
issues
Imp A
Imp B

## Slide 7
PROGRESS: Post Lab Key activities (tasks) up to Dec 31, 2014 | Start date | End date | Status
FINALIZATION OF THE TOOL FOR STAR RATING OF HEALTH FACILITIES |  |  | 
Incorporation of feedback from Kisarawe Pilot | November 3, 2014 | November 10, 2014 | Done
Syndication with RBF team members and agreed to incorporate RBF elements into Star Rating Tool (SRT) | November 7, 2014 | November 21,2014 | Done
MoHSW team (HSIQAS, RBF and PSS) worked with IHI team to finalize the SRT | November 24, 2014 | November 28, 2014 | Done
Syndication with ICT team to work on database development | December 8, 2014 | December 8, 2014 | Done
MoHSW team (HSIQAS, RBF, PHAB, DCS, PSS and ICT) and IHI worked on scoring of the SRT | December 10, 2014 | December 11, 2014 | Done
Trial run of the SRT in Mkuranga district done | December 17, 2014 | December 24, 2014 | Done
Identification of National and District level assessors from both public and private institutions | District level done for 21 councils |  | Done for National Assessors
Completion of work plan and budget for nationwide assessment | Ongoing |  | Done

## Slide 8
PROGRESS:Key activities (tasks) from January 1 to 31st March 2015 | Action party | Start date | End date | Status
Orientation of the 160 national team. The orientation will be on the SRT, data base and data entry | HSIQAS-MoHSW | January 5, 2014 | January 9, 2014 | These tasks are not yet done due to challenge of funding
National team to orient the regional assessment team ( 6 per council). The orientation will be on the SRT, data base and data entry | National team | January 12 , 2015 | January 16, 2015 | 
Assessment of all primary health facilities at district level (hospital at district level, Health Centre and dispensaries) Data entry on daily basis Proposed QIP for each facility for implementation | National and Regional team | January 19, 2015 | February 27, 2015 | 
All facility plans and budgets to be consolidated by CHMT and incorporated in the Comprehensive Council Health Plan (CCHP). | Assessors’ team leads/CHMT | March 2, 2015 | March 14, 2015 | 
Develop a detailed implementation plan to roll out the intervention program in the 12 regions | HSIQAS-MoHSW | March 16, 2015 | March 31, 2015 | 

## Slide 9: REACHING THE REGIONS, COUNCILS AND HEALTH FACILITIES (1/3)
PMO-RALG –Will be involved as national assessors
RHMTs –
  Will be oriented on BRN and the SRT before training of LGA assessors
  2 or 3 RHMT members will be accompanying assessment teams at LGA level. (so as not to disrupt RHMT functioning)
CHMTs
  will be oriented on the tool
  will accompany assessment teams ( 1 CHMT member for each team)
  will incorporate the QIP into the CCHP
  will do quarterly supportive supervision
  will report to higher level (regional and national level)
Health Facilities
  Will support assessment teams
  Will implement QIPs

## Slide 10: REACHING THE REGIONS, COUNCILS AND HEALTH FACILITIES (2/3)
National assessors
MOHSW- HQAD, DCS, PHAB, DPP, PPP, DPS, Social welfare, NHLQATC
PUBLIC HOSPITALS - MUHAS, OCEAN ROAD HOSPITAL, LUGALO HOSPITAL
PARTNERS – JHPIEGO, APHFTA, THPS, EGPAF, PATHFINDER, CDC, IHI, GIZ, CSSC,
Local Government Assessors
1104 assessors to be identified from the councils
Health care personnel from public and private facilities

## Slide 11: REACHING THE REGIONS, COUNCILS AND HEALTH FACILITIES (3/3)
REGIONS | LGAs | NATIONAL ASSESSORS | TEAMS ON THE DISTRICT LEVEL | ASSESSORS PER REGION
ARUSHA | 7 | 7 | 9 (CITY & MERU 2 TEAMS EACH) | 54
DODOMA | 6 | 6 | 7 (DODOMA MC -2 TEAMS) | 42
TEMEKE | 3 | 2 | 3 | 18
ILALA | 4 | 2 | 4 | 24
KINONDONI | 5 | 2 | 5 | 30
GEITA | 4 | 4 | 4 | 24
IRINGA | 6 | 6 | 6 | 36
KAGERA | 8 | 8 | 8 | 48
KATAVI | 2 | 2 | 2 | 12
KIGOMA | 6 | 6 | 7 (KIBONDO -2 TEAMS) | 42

## Slide 12: M & E AND MONITORING INDICATORS
Supportive supervision will be done quarterly by the CHMT to oversee QIP
  Reports to be sent to higher levels
Star rating re-assessment triggered by CHMT based on QIP progress and self assessments.
Star rating re-assessment after one year
Indicators
  Number(and %) of health facilities assessed and star rated
  Number(and %) of facility specific QIPs developed
  Number(and %) of facilities which have done quarterly self assessment
  Number(and %) of councils which have incorporated QIPs into the CCHP

## Slide 13: BUDGET FOR ASSESSMENT OF THE WHOLE COUNTRY
ACTIVITIES | TSHS
DEVELOPMENT OF DATABASE | 186,100,000
TABLETS FOR DATA COLLECTION | 288,000,000
TRAINING OF 160 NATIONAL ASSESSORS | 126,514,000
TRAINING OF 1104 ASSESSORS | 1,271,061,660
CHMT AND RHMT (escorting assessment teams) | 535,500,000
ASSESSMENT | 3,649,904,700
TOTAL | 6,057,080,360

## Slide 14: CHALLENGES
          Availability of adequate funding to implement BIG BANG (5,582,980,360)
            So far available funding is 1.67 billion in the PMO- RALG, BHSP account earmarked for capacity building in all 167 LGAs ( 10 million per LGA )
Database development
      DHIS Interfacing with star-rating and quality indicators database
  Needs funding, time is not with us

## Slide 15: WAY FORWARD
DPs and implementing partners support to leverage the costs for Big Bang

## Slide 16
THANK YOU FOR LISTENING