TANZANIA MAINLAND

Ministry of Health and Social Welfare

Policy and Planning Department

Monitoring and Evaluation Section

# Foreword

This Health Sector Performance Profile Report 2011 presents the assessment of health system performance in Mainland Tanzania for the financial year 2010/11. It summarises the effectiveness of inputs, processes, outcomes and their impact on the health system, measured by indicators from the Health Sector Strategic Plan III.  In this way progress towards the National Health Policy objectives and international commitments can be measured with a high degree of certainty. The monitoring and evaluation process also identifies areas where performance has been lower than the expected target, requiring remedial measures to be taken on a continual basis.

This year’s report presents updates on indicator areas included in the last year’s Performance Assessment report, showing trends, progress towards targets and, in some cases, regional variations.  The major components of the assessment are:

- Performance in the 46 health sector performance indicators (including MDGs, MKUKUTA and PAF indicators),

- Assessment of progress towards achieving the Milestones outlined at the September 2011 Joint Annual Health Sector Review meeting,

- Implementation status of the MOHSW Medium Term Expenditure Framework (MTEF)

- Assessment of health service performance at the Council level

- Highlights of the Public Expenditure Review for the Health Sector for FY2009/10

- Assessment of the current status of Human Resources for the sector; and

- Conclusions (including outstanding issues and challenges)

To accomplish this work, every effort has been made to assemble available information, check it, and report accurately on every aspect. Multiple sources of information have been used. The milestone assessment provides information on achievements registered during the period of one year. The MTEF report draws upon the implementation status of all activities in the 2010/11 financial year MOHSW plan and budget (grouped according to vote number). The health financing section draws from the latest health sector Public Expenditure Review while the section on Council Health Sector performance draws upon the analysis of 21 Regional reports covering the implementation progress of the 132 Comprehensive Council Health Plans (CCHPs). The chapter on Human Resources includes, for the first time, information captured by the Human Resources Information System software.

Reporting on the 46 health sector performance indicators, data came from a number of sources including HMIS, PER, TDHS 2010/11 and reports from various health programs (e.g. TB and Leprosy, NACP, NMCP, EPI, Reproductive and Child Health etc.

While this report significantly contributes to the MOHSW efforts towards effective and sustainable M&E, the scope of the analysis has been limited by some constraints, notably problems with the availability of robust and credible routine data. This chronic weakness highlights the critical importance of strengthening Health Information Systems particularly HMIS through M & E Section.

The work devoted to the construction and publication of this report was conducted under the coordination of the Directorate of Policy and Planning through the Monitoring and Evaluation Section and Working Group in collaboration with Joint Annual Health Sector Review Organizing Committee. Many thanks are extended to all who participated in one way or another in this endeavor particularly MoHSW staff and M & E Working Group.

Regina L. Kikuli

Ag. Permanent Secretary,

Ministry of Health and Social Welfare, Mainland Tanzania

# Acronyms

ANC		Antenatal Clinic

ART		Antiretroviral Therapy

CCHP		Comprehensive Council Health Plan

CFS		Consolidated Fund Services

CHF		Community Health Fund

CHMT		Council Health Management Team

DDH		District Designated Hospital

DPP		Department of Policy and Planning

EmOC		Emergency Obstetric Care

FBO		Faith Based Organization

HMIS		Health Management Information System

HSF		Health Services Fund

HSSP III	Health Sector Strategic Plan III

HRIS		Human Resource Information System

ILS		Integrated Logistics System

IMCI		Integrated Management of Childhood Illness

iPTP		Intermittent Presumptive Treatment (for pregnant mothers)

ITN		Insect side Treated Net

JAHSR		Joint Annual Health Sector Review

LGA		Local Government Authority

MKUKUTA	Mkakati wa Kukuza Uchumi na Kupunguza Umaskini Tanzania

MMAM	Mpango wa Maendeleo wa Afya ya Msingi

MMR		Maternal Mortality Ratio

MOFEA	Ministry of Finance and Economic Affairs

MOHSW	Ministry of Health and Social Welfare

MSD		Medical Stores Department

MTEF		Medium Term Expenditure Framework

NACP		National AIDS Control Programme

NACTE	National Council of Technical Education

NBS		National Bureau of Statistics

NGO		Non-Governmental Organisation

NHIF		National Health Insurance Fund

OPD		Outpatient Department

P4P		Pay for Performance

PER		Public Expenditure Review

PMO-RALG	Prime Minister’s Office-Regional Administration and Local

Government

PMTCT	Prevention of Mother to Child Transmission

POPSM	President’s Office, Public Service Management

PPP		Public Private Partnership

RCH		Reproductive and Child Health

RDT		Rapid Diagnostic Test (for malaria)

RHMT		Regional Health Management Team

STI		Sexually Transmitted Infection

SWAp		Sector Wide Approach

TB		Tuberculosis

TDHS		Tanzania Demographic and Health Survey

THMIS		Tanzania HIV/AIDS and Malaria Indicator Survey

TIKA		Tiba kwa Kadi

Contents

Foreword	2

Acronyms	4

Chapter 1: Introduction and Overview	9

Chapter2:  Health Sector Performance Indicators	12

Progress towards Health Status of the Population	12

Progress towards Service Delivery	16

Progress against indicators in the Performance Assessment Framework matrix	32

Chapter 3:  Summary of Progress against the Milestones agreed at Joint Annual Health Sector Review 2010	34

Chapter 4: MTEF Implementation performance 2010/11	43

Chapter 5: Council health performance	44

Chapter 6: Health system indicators, including health financing and expenditure	56

Basic Expenditure Performance Indicators for the Public Health Sector in Tanzania	56

Expenditure Trends: Recurrent Vs Development from 2005/06 – 2010/11	59

Public Health Expenditure by Financing Sources	61

Budget Performance in the Health Sector	62

Expenditures by Key Intervention Areas	65

Pharmaceuticals	70

Chapter 7: Human Resource Status in the Health Sector	76

Chapter 8: Conclusion	85

Issues and challenges	85

Areas of good performance	85

Annex I: HSSP III Indicators up to 2010	86

Annex II: Performance of Health Status Indicators	96

Annex III: OPD Attendance per capita by region in 2010	98

List of Tables

Table 1: Proposed Formats for Health Sector Performance Profile Report	9

Table 2: Performance of Health Status Indicators	12

Table 3: Trends in malaria indicators	27

Table 4 PAF indicators for 2010/11	33

Table 5 HRH budget allocation	42

Table 6 MTEF implementation status (Recurrent) in 2010/11	43

Table 7 Top and Bottom 10 of Health Fund Allocations by Councils	48

Table 8 Number of health Facilities by type and ownership in Mainland Tanzania by June 2011	50

Table 9: Per capita expenditure performance indicators for the public health sector	56

Table 10: Local Government health spending	57

Table 11: Selected health sector financing indicators in USD	58

Table 12: Expenditure Trends: Development Vs Recurrent (TZS billion)	60

Table 13: Trend of total public spending on health (Billion TZS)	61

Table 14: Source of funds for the public health sector (TZS billion)	62

Table 15: Budget performance – recurrent vs development	63

Table 16: Budget performance: Government vs foreign funds	63

Table 17: MOHSW budget performance by departments, FY2009/10	64

Table 18: MOHSW expenditures by key intervention area, 2009/10	65

Table 19: MKUKUTA-related expenditures, 2009/10	66

Table 20: Health Expenditures among Layers of Government	67

Table 21: Health sector expenditure by the categories of spending units	67

Table 22: Real per capita budget for essential medicines (five years)	71

Table 23: Allocation of the essential medicines funds by level, FY2010/11	73

Table 24 Quarterly availability of tracer medicines (10 quarters, 2009 to 2011)	74

Table 25: Trend in availability of tracer medicines (2009 to 2011)	75

Table 26: Available health workers	76

Table 27: Staff in national, referral and specialised hospitals	76

Table 28: Enrollment into training schools	77

Table 29: HR position in selected locations, 2010	78

Table 30: Accreditation status of Health and Allied Sciences training institutions	84

List of figures

Figure 1: Neonatal, Infant and Under-five mortality rates	13

Figure 2: Maternal Mortality Ratio, Mainland Tanzania 1999-2010	14

Figure 3: Life expectancy at birth from Rufiji DSS	15

Figure 4: Nutritional Status Mainland Tanzania TDHS 2004/05-2010	16

Figure 5: OPD attendance per capita	17

Figure 6: Measles vaccination by region, 2010	18

Figure 7 Proportion of children under one vaccinated 3 times against DPT –Hb3	19

Figure 8: Proportion of children under one vaccinated 3 times against DPT –Hb3 from 2001 up to 2010	19

Figure 9: Tetanus Toxoid vaccination by Region in 2010	20

Figure 10: Pregnant women starting ANC before 16 weeks of gestation age	21

Figure 11: Births attended in health facility by Region in 2010	22

Figure 12: Causes of maternal deaths in health facilities, 2010	24

Figure 13: percentage of HIV positive women receiving ARVs in 2010	25

Figure 14: Proportion of patients on treatment and care receiving ARVS by region in 2010	25

Figure 15: Trends in children enrolled and on ART 2008-2010	26

Figure 16: Trends in Adults enrolled and on ART, 2008-10	26

Figure 17: IPTp coverage in recent household surveys	28

Figure 18: Use of ITN for both Under-five and Pregnant Women	29

Figure 19: prevalence of malaria parasitaemia in Under-fives	30

Figure 20: Tuberculosis notification rate	30

Figure 21: TB treatment success rate by region, 2010	31

Figure 22: Leprosy treatment completion, 2009	32

Figure 23: CCHP 2011/12 performance per region	44

Figure 24: Allocation of Delivery Kits per regions	46

Figure 25: Total amount allocated to each Priority Area	47

Figure 26: Percent of total budget allocated in the CCHP by region	48

Figure 27: CCHP Funding Sources in Percent	49

Figure 28: Percent of health facilities by type in Tanzania Mainland 2010/11	49

Figure 29: Human Resources per LGA, 2010/11 – as per Establishment	51

Figure 30: Human resource deficit in each region by June 2010 (all cadres combined)	51

Figure 31: Trend of TB cases in 2008, 2009 and 2010	52

Figure 32: Trend of HIV cases and patients on ARVs	53

Figure 33: Trend of PMTCT and VCT	53

Figure 34: Trend of births attendance at health facility and community delivery since year 2008	54

Figure 35: Trend in Antenatal Care attendance rate since year 2007	54

Figure 36 Severe malnutrition rates from CCHP assessment	55

Figure 37: Five year trend in the budget for essential medicines	71

Figure 38: Execution of the essential medicines budget over four financial years	72

Figure 39: Budget performance by source of funds over four financial years	72

Figure 40:  Medical Officers and Assistant Medical Officers per 10,000 population, by region, 2010	79

Figure 41: Nurses and midwives per 10,000 population, by region, 2010	80

Figure 42:  Pharmacy staff per 10,000 population, by region, 2010	81

Figure 43: Health officers per 10,000 population, by region, 2010	82

Figure 44:  Laboratory staff per 10,000 population, by region, 2010	83

HEALTH SECTOR PERFORMANCE PROFILE REPORT 2010/11

# Chapter 1: Introduction and Overview

This report provides an overview of health sector progress and performance during financial year 2010-2011. It follows the Ministry of Health and Social Welfare’s (MOHSW) format for health sector performance profile which closely mirrors the Ministry of Finance (MOF) format for annual performance reports (as summarized in Table 1 below). The main departure from the MOF‘s format is an attempt to capture information on Council’s performance.

Table 1: Proposed Formats for Health Sector Performance Profile Report

| Ministry of Finance Format | Health Sector Performance Profile Update |
| --- | --- |
| Part 1: Foreword, Introduction | Chapter 1: Introduction & overview |
| Part 2: Health Sector Performance Indicators | Chapter 2: Progress against 46 health sector indicators |
| Section 2.1 Progress towards Health Systems | Progress towards Health Status Progress in improving Service Delivery |
| Section 2.2 Progress in improving Service Delivery |  |
| Section 2.3 Progress in Health Status |  |
| Section 2.4 Milestones/Priority Interventions | Chapter 3: Milestones Report |
| Section 2.5 Issues, challenges | See concluding chapter |
| Part 3: Achievement of Annual Targets | Chapter 4: MTEF Implementation Status |
| n/a | Chapter 5: Review of Council Health Performance |
| Part 4: Expenditure | Chapter 6: Highlights from the Public Expenditure Review Update |
| Part 5: Human Resources Review | Chapter 7: Human Resource Status in the Health Sector |
|  | Chapter 8: Conclusion, Issues & Challenges |

This report is intended to provide an objective, evidence-based assessment of performance with reference to official indicators and targets as set in the Health Sector Strategic Plan III (HSSPIII). The data reported here come from a variety of official sources, including:

- Service delivery statistics from Ministry of Health and Social Welfare (MOHSW)

- Expenditure data from the Public Expenditure Review (PER) update for FY2009/10

- MOHSW, annual implementation report (Physical and Financial) for 1st July 2010 to 30th June 2011

- Milestone implementation status report from Joint Annual Health Sector Review Report (November 2011).

- Human resource (HR) data collected retrieved from HR Management Information System by the MOHSW through District Medical Offices

- Tanzania Demographic and Health Survey (2010/11) report

- Draft report on Comprehensive Council Health Plans (CCHP) 2010/11

- UNICEF’s situation analysis report in health, water and sanitation for Tanzania Mainland 2009

Chapter 2 on the Health Sector Performance Indicators presents the latest information on the agreed HSSP III health sector indicators. These comprise a mix of input, output, outcome and impact indicators grouped as follows:

- Progress towards Health Status of the Population

- Progress towards Service Delivery

- Progress against PAF indicators

Details of the specific indicators are given in the relevant sections of the Chapter.

A number of the indicators are also used to measure progress towards the health-related Millennium Development Goals (MDGs), and also the Performance Assessment Framework (PAF) for General Budget Support.  These are also highlighted in Chapter 2.

Chapter 3 provides a summary of progress against the Milestones that were agreed at last year’s Joint Annual Health Sector Review (2010)

Chapter 4 examines implementation performance against the strategies, objectives and targets set out in the Medium Term Expenditure Framework (MTEF) of the MOHSW for financial year 2009/10.

Chapter 5 reviews Council health performance, drawing upon the Regional/Central review of Council Comprehensive Health Plans (CCHPs) and their implementation.  This analysis is undertaken using assessment criteria for compliance and performance to the guidelines.

Chapter 6 provides a number of additional health sector spending and financing indicators, drawn from the FY2009/10 Public Expenditure Review (PER) update, together with information on pharmaceutical availability and spending.

Chapter 7 summarises information on Human Resources for Health, while Chapter 8 concludes the report by highlighting areas of good performance and also selected issues and challenges.

# Chapter2:  Health Sector Performance Indicators

## Progress towards Health Status of the Population

This sub-set of the HSSP III indicators is meant to measure the performance of the health status of key population groups. This thematic area includes:-

- Neonatal Mortality Rate

- Infant Mortality Rate

- Under Five Mortality Rate

- Nutritional Status

- Maternal Mortality Ratio

- Life expectancy at birth

- Total Fertility Rate

Recent performance, together with the 2015 targets, is shown in Table 2 below.

Table 2: Performance of Health Status Indicators

| NO. | INDICATOR | Other Sources | TDHS (04/05) | THMIS (07/08) | TDHS 2010 | TARGET 2015 |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Neonatal mortality rate (per 1,000 live births) |  | 32 | 29 | 26 | 19 |
| 2. | Infant mortality rate (per 1,000 live births) |  | 68 | 58 | 51 | 43 |
| 3. | Under-five mortality rate (per 1,000 live births) |  | 112 | 91 | 81 | 54 |
| 4. | Proportion of under-fives who are underweight |  | 22% |  | 16% | 14% |
| 5. | Proportion of under-fives who are stunted |  | 38% |  | 42% | 22% |
| 6. | Maternal mortality ratio (per 100,000 live births |  | 578 |  | 454 | 265 |
| 7. | Life expectancy at birth | 52 (F) 51 (M) (Census 01/02) |  |  |  | 62 (F) 59(M) (by 2025) |

The above table shows the indicators used to measure the health status of the population. It is worth noting that most of the data needed to measure these indicators are collected periodically, thus some have been updated using the TDHS 2010, while other indicators will be measured with other type of surveys to be conducted in the near future. For missing data, proxy indicators have been supplemented by routine data from the HMIS which is largely health facility data and which has the limitation of exclude those data from referral and central hospitals.

### Neonatal, Infant and Under Five Mortality Rate

Table 2 above presents levels, trends, and differentials in Neonatal, Infant and Under-five mortality in Tanzania. The information enhances understanding of population trends and will assist in the planning and evaluation of health policies and programs. Estimates of infant and under-five mortality rates can be used to develop population projections. Information on under-five mortality also serves the need of the health sector to identify population groups that are at high risk. The analysis in this report provides an opportunity to evaluate the performance of programs of the Ministry of Health and Social Welfare aimed at reducing infant and child mortality. Furthermore, infant and under-5 mortality rates are used to assess the National Strategy for Growth and Reduction of Poverty (NSGRP).

Neonatal mortality measures the probability of dying in the first month of life, while Infant mortality is the probability of dying before the first birthday and Under-five mortality provide probability of dying before the fifth birthday. These indicators reflect a country’s level of socio-economic development and quality of life. Analyzing these three indicators it can potentially predict the overall performance of the health sector. The rise or decline of these indicators is attributed to various social economic factors. The results from TDHS 2009/10 shows significant decline of child mortality specifically infant and Under Five Mortality Rate (Figure 1). However, high neonatal deaths remain a significant challenge in Tanzania.

Figure 1: Neonatal, Infant and Under-five mortality rates

### Maternal Mortality Ratio

Maternal Mortality is defined as any death that was reported as occurring during pregnancy, childbirth or within two months after the birth or termination of a pregnancy.

The estimate of the Maternal Mortality Ratio (MMR) for the 10 years period preceding the survey is estimated as 454 maternal deaths per 100,000 live births. In other words for every 1,000 in Tanzania during the period about four to five women died of pregnancy related causes.

The Maternal mortality ratio is measured periodically through Tanzania Demographic and Health Surveys (TDHS). The TDHS 2004/05 estimated Maternal Mortality Ratio (MMR) at 578 maternal deaths per 100,000 live births.  The TDHS results of 2009/10 shows MMR has declined to 454 deaths per 100,000 live births. This is a notable improvement but relatively the maternal deaths are still high requiring more effort to attain MDG goal which is 265 per 1000,000 live births.  Also, the same goal is used for the MKUKUTA target.

Figure 2: Maternal Mortality Ratio, Mainland Tanzania 1999-2010

### Life expectancy at birth

Life expectancy is the estimate of the average number of additional life years a person could expect to live if the age-specific death rates for a given year prevailed for the rest of his/her life.  It is a hypothetical measure because it is based on current death rates and actual death rates change over the course of a person’s lifetime. Results from previous population censuses show that life expectancy rate has been increasing very slowly. In 1978, life expectancy in the United Republic of Tanzania (URT) was recorded at 44 years. It rose to 50 in 1988 and increased slightly to 51 in 2002. These estimates are well below the expected life expectancy of 56 and 58 years which was earlier projected.

Although the prevalence of major diseases appears to be declining, the current HIV/AIDS prevalence rate may have been one of the major contributors to the slow increase of life expectancy in Tanzania. However, with substantial decline in child mortality, it is projected that on average, people in Tanzania have improved their life expectancies significantly. A good example of the measured change in child mortality is demonstrated by the Rufiji Demographic Surveillance Site (DSS) in Coast region.  As a result of effective to health interventions delivered between1999 and 2007, child mortality declined remarkably. In fact, the reduction in child mortality increased life expectancy by 5-10 years during the surveillance period (Figure 3). Using National Bureau of Statistics (NBS) projections, it is now estimated that life expectancy in 2010 is around 57 for males and 59 for females. This will be confirmed by the 2012 population census results.

Figure 3: Life expectancy at birth from Rufiji DSS

### Nutritional Status

The 2010 TDHS measured three anthropometric indicators of nutritional status in children. These are Height for Age, Weight for Height and Weight for Age.  At National level 42% of children under five have low Height for Age or are stunted, 5% have low Weight for Age or are wasted, and 16% have low Weight for age reflects both chronic and acute under nutrition. These results reflect a mix in progress in nutritional status from the 2004/05 TDHS when these indicators were measured at 38%, 3%, and 22% respectively.  This implies no improvement on nutritional status indicators as per MKUKUTA target and 2015 HSPSIII target, which means more effort is needed to achieve both targets for stunting and wasting.

Figure 4: Nutritional Status Mainland Tanzania TDHS 2004/05-2010

## Progress towards Service Delivery

Service delivery indicators include outpatient attendance, vaccination coverage, access to reproductive health services, and indicators measuring HIV and AIDS, malaria, tuberculosis and leprosy, infectious and non-communicable disease performances.

### Outpatient attendance per capita

One of the key indicators to assess performance on the provision of health services in Mainland Tanzania is to understand the number of people attending and receiving services at health facilities during periods of illness.  A good indicator of this is the outpatient attendance per capita. This indicator shows the extent of facility utilization by the population. If Out Patient Department (OPD) attendance is found to be high in the public health facilities, it implies that the population is able to access and is broadly satisfied by provision of services in these facilities.  Figure 5 below displays the OPD attendances per capita in Mainland Tanzania regions. It is calculated using the 2010 population projections from the individual regional reports from NBS.  The OPD attendance per capita is highest in the Dar es Salaam (1.39) and Tanga (1.33) regions.  The three lowest OPD per capita rates are observed in Mtwara, Kagera and Tabora, where the figure is only slightly over 0.5 attendances per capita (Annex III shows regional figures). The Tanzania Mainland average OPD attendance per capita is 0.84 which is a substantial increase over the figure of 0.74 the previous year. This also indicates that the 2015 HSPS III target of 0.80 has been surpassed.

Figure 5: OPD attendance per capita

### Measles Vaccination

This indicator measures the percentage of the total number of children below one year of age vaccinated against measles in a given population. It enables monitoring of immunization of children against the preventable diseases. Immunization is considered to have a high impact on child mortality reduction.  The numerator for this estimation is calculated using the total number of children under one year vaccinated against measles in the numerator while the denominator is comprised of the total number of Children Under one year in a specified year.

Measles vaccination performance was 88 % in 2008, and increased to 91 % in 2009, and has slightly dropped to 90.2 % in 2010, and this indicator value is still well above the HSSP III 2015 target of 85 %. Despite these gains, seven regions (Arusha, Mara, Kagera, Kigoma, Kilimanjaro, Ruvuma and Pwani) scored below the HSSP III 2015 target of 85 %, as shown in Figure 6 below, and they need to improve their performances; with Ruvuma (73.8 %) and Kagera (75.2 %) scoring the lowest.

Figure 6: Measles vaccination by region, 2010

Nationally, measles coverage has remained high at 90% which is above the target (Source HMIS: 2010)

### DPT_HB3 Vaccination

Measurement for DPT_HB3 is defined as the proportion of children under one year vaccinated 3 times against three antigens. By 2004, the DPT-HB3 coverage peaked at 94%. Unfortunately, this was followed by a sharp decline to 83% in 2007. However, 2008 saw an increase by 3 percentage points or 86%. In 2009, the DPT-HB3 coverage was 85.7%, and in 2010 it slightly increased to 89.6 %; and this performance is above the HSPS III 2015 target of 85 %. In year 2010, eight regions (Arusha, Kilimanjaro, Tanga, Tabora, Kigoma, Pwani, Rukwa, and Ruvuma) scored a DPT-HB3 vaccination performance below the HSPS III 2015 target of 85 %, as shown in Figure 7 below.  Ruvuma (71.8 %) and Rukwa (79.5 %) scored the lowest, calling for further improvement of this intervention.

Figure 7 Proportion of children under one vaccinated 3 times against DPT –Hb3

Figure 8: Proportion of children under one vaccinated 3 times against DPT –Hb3 from 2001 up to 2010

### Tetanus Toxoid 2+ Vaccination

Tetanus toxoid injections (TT2+) are given during pregnancy to prevent neonatal tetanus, an important cause of infant deaths. The injections are an important part of antenatal care. Because of this, the MoHSW advocates for all women of reproductive age are vaccinated before they become pregnant. Tetanus is still a relatively common cause of death among newborns in Tanzania; indicating a need for more efforts devoted to increasing vaccination coverage and safer delivery practices. Generally, health facility reports reveal that the percentage of pregnant women receiving the TT2+ vaccine decreased from 85 percent in 2008 to about 73.1 percent in 2009, and then slightly increased to 76.8 % in 2010. The current status of vaccination performance is provided in Figure 9 showing remarkable regional differences. Whereas the HSPS III 2015 TT2+ target is 85 %, only five regions (Dar es Salaam, Tanga, Rukwa, Arusha, Kilimanjaro and  Morogoro, ) scored above this target.

Figure 9: Tetanus Toxoid vaccination by Region in 2010

### Proportion of pregnant women starting ANC before 16 weeks of gestation age

Antenatal care can be most effective in avoiding adverse pregnancy outcomes when it is sought early in the pregnancy and continues through to delivery. Early and regular checkups by trained medical providers are very important in assessing the physical status of women during pregnancy. In 2008 about a sixth (14%) of pregnant women started attending ANC services before 16 weeks of gestation, whereas in 2009, slightly less than a half (47%) attended ANC services before 16 weeks of gestation.  In 2010, this proportion dropped to 45.7 % as presented in Figure 10 below. No target was set for this indicator in the HSSP III, however, the Reproductive Health Strategy 2005 to 2010 did set a target of 60% of pregnant women starting attending ANC services before 16 weeks of gestation by end of year 2010), the current performance is significantly behind the RCH target; which implies that a more intervention is needed and required.

Figure 10: Pregnant women starting ANC before 16 weeks of gestation age

### Proportion of pregnant women attending ANC at least 4 times during pregnancy

This indicator is defined as the number of pregnant women attending ANC at least 4 times during pregnancy as a proportion of the total number of pregnant women in a given population. Under normal circumstances, WHO recommends that a pregnant woman without complications have at least four ANC visits to provide sufficient care. It is possible during these visits to detect reproductive health risk factors. In the event of any complication, more frequent visits are advisable and admission to a hospital may become necessary. The results from the 2004/05 TDHS show that 98% of pregnant women attended at least one ANC visit during that time; and 69.5 % of pregnant women attended ANC at least 4 times during pregnancy. The results from the 2010 TDHS show that only 43 % of women whose last birth occurred in the five years before the survey made four or more ANC visits, and this is a sharp decline from the percentage recorded in the 2004-05 TDHS.

### Proportion of births attended in health facility

Proper medical attention and hygienic conditions during delivery can reduce the risk of complications and infections that can cause the death or serious illness of the mother and/or the newborn baby. Thus, another important component of efforts to reduce health risks to mothers and new born children is increasing the proportion of babies that are delivered in facilities. The proportion of births attended in a health facility is calculated by taking the number of deliveries conducted in health facilities as the percent of the projected number of births. Health facility data (HMIS) on reproductive health show that in 2009 more than half (54 %) of deliveries occurred at health facilities, and this slightly increased to 58.4 % in year 2010 as presented in Figure 11 below. This data indicate that there has been a gradual but steady increase of deliveries conducted at health facilities from 51% and 52% in 2007 and 2008, respectively. These findings show that more effort is required to achieve the 2015 HSSP III target.

As shown in Figure 11, four regions (Dar es Salaam, Kilimanjaro, Ruvuma and Iringa) scored above the 2015 HSSP III target.  The impressive performance in these regions means, however, that the majority perform below the national average.   Tabora (30.8 %) and Manyara (24.2 %) had the poorest performance.

Figure 11: Births attended in health facility by Region in 2010

Source: TDHS 2010

The 2004/05 TDHS found that 47 % of deliveries were at health facilities, and in the 2010 TDHS only half (50.2 %) of the deliveries were at health facilities, the majority of them (41 %) at public health facilities. The TDHS data shows that there is no much difference between household/community based data to that compiled at the health facilities (HMIS).

### Proportion of births attended by skilled health personnel

The type of assistance a woman receives during childbirth has important health consequences for both mother and child. The proportion of births attended by skilled health personnel is measured by the number of deliveries conducted by skilled health personnel as a proportion of projected number of births. The 2004/05 TSDHS findings showed that less than half (46%) of births or deliveries were attended by skilled attendants; whereas the 2010 TDHS reports that 51% of deliveries were attended by skilled attendants, indicating a slight increase.

### Contraceptive prevalence rate

The level of current use of contraceptive methods is one of the indicators most frequently used to assess the success of family planning programme activities and one of the determinants of fertility. This indicator is measured as number of contraceptive active users (including and excluding condom) as a proportion of the total number of women of child bearing age. In 2010 data from facility (HMIS) indicated that 46.7 % of the women of reproductive age were using any modern family planning method. However, the 2004/05 TDHS found that 20% of married women were using any modern contraceptive method, and this slightly increased to 27% five years later as reported by the 2010 TDHS. These findings indicate there is still a big gap that needs to be filled when this attainment is compared to the 60% contraceptive prevalence rate by 2015 stipulated in the Maternal Neonatal and Child Health (MNCH) Strategic Plan 2008-2015 (One Plan).

### Maternal Case Fatality Rate in Health Facilities

This indicator measures the number of deaths due to maternal complications as a proportion of the number of women admitted due to maternal complications. Until now, routine data collection captures the number of deaths due to maternal complications but does not report the number of women admitted due to maternal complications. Given this situation, the available information on number of deaths due to maternal complications and causes will be used to calculate each cause as a proportion of total maternal deaths, and will be used as a proxy for maternal case fatality rate. Available information from HMIS for year 2009 indicated that the highest number of maternal deaths was reported in Mwanza (176), Tabora (164), (153) and Dar es Salaam (137) regions; and the regions with the lowest number of maternal deaths included Pwani (30), Arusha (32) and Lindi (39). During year 2009, the major causes of facility based maternal deaths included Post Partum Hemorrhage (22 %) followed by eclampsia (13 %) and anemia (9 %).

During year 2010, HMIS captured a total of 1,797 facility based maternal deaths on Tanzania mainland. The regions with the highest number of facility based maternal deaths were Rukwa (101), Dar es Salaam (106), Mbeya (122), Tabora (130), Mwanza (175), and Shinyanga (175); whereas the regions with the lowest number of number of facility based maternal deaths were and Singida (58), Kigoma (51), Kilimanjaro (50), Lindi (41), Arusha (36), and Manyara (37).

During year 2010, the major causes of facility based maternal deaths included PPH (20 %), eclampsia (14.1 %), anaemia (10 %), septicemia (6.9 %), APH (5.6 %), and puerperal sepsis (5.6 %) as presented in Figure 12 below. This data indicate that the pattern of the major causes of facility based maternal deaths during 2010 did not change much as compared to year 2008 and 2009.

Figure 12: Causes of maternal deaths in health facilities, 2010

### Percentage of HIV positive women receiving ARVs

This indicator measures the number of HIV positive women receiving antiretroviral (ARV) drugs for Prevention of Mother to Child Transmission (PMTCT) as a proportion of the total number of HIV positive pregnant women per year. Figure 13 shows about 92.4 of HIV positive women were receiving ARVs to prevent MTCT in 2010; an increase from 43% in 2009 (RCH, 2009).  Assessing regional variation, the majority of regions have achieved the 2015 HSPSIII target of 80%. However, dismal performances were recorded in Morogoro (66.5%).

Figure 13: percentage of HIV positive women receiving ARVs in 2010

Source: NACP 2010

### Number of persons with HIV infection receiving ARV combination therapy

By the end of December 2010, 384,816 people were receiving ART,  which is an increase from 303,664 in 2009 (Appendix XI). Despite a notable increase, this is below the National AIDS Control Program (NACP) target of 440,000 patients by 2010 and this is equivalent to 87.4% of the target. On average, 52% of persons with HIV infections receiving care and treatment are receiving ARVS. Assessing the regional variations, the regions of Dodoma, Dar es Salaam and Singida have the highest proportion receiving ARVS while Tabora and Kigoma regions have lowest proportions receiving ARVS, as shown in Figure 14.

Figure 14: Proportion of patients on treatment and care receiving ARVS by region in 2010

Figures 15 and 16 below show the trend in the number of children and adults enrolled and receiving ART respectively.

Figure 15: Trends in children enrolled and on ART 2008-2010

Figure 16: Trends in Adults enrolled and on ART, 2008-10

There has been a notable increase of adults both enrolled and ART from 2008 to 2010 of about 100%

### Malaria

Malaria is one of the major public health problems in Tanzania affecting the health and welfare of Tanzanians. Health facility based statistics show that malaria is the leading cause of morbidity and mortality, especially in children under five years with high socioeconomic impact contributing to poverty and underdevelopment.

The Government’s Medium Term Malaria Strategic Plan 2008-2013, which builds on previous plan 2002 – 2007, aims to reduce the burden of malaria by 80% by the end of 2013 from the 2007 levels. As a result of increased partnership and commitment in rolling back malaria, investment in malaria control increased and enabled rapid scaling up of recommended cost effective interventions. Health facility data and periodic household surveys - TDHS and THMIS, provide information required to assess progress and impact of the interventions towards achieving national and international targets, also to account for the increased funding.  Core indicators and progress made is summarised in Table 3 below, with more details in the subsequent text.

Table 3: Trends in malaria indicators

| Indicator | Value (%) TDHS 2004/05 | Value (%) THMIS 2007/08 | Value (%) TDHS 2009/10 |
| --- | --- | --- | --- |
| Proportion of mothers who received two doses of preventive intermittent treatment for malaria during last pregnancy | 22 | 30 | 27 |
| Proportion of vulnerable groups (pregnant women 15-49 years of age) sleeping under an ITN previous night | 15 | 27 | 57 |
| Proportion of vulnerable groups (children under 5) sleeping under an ITN previous night | 16 | 26 | 64 |
| Proportion of laboratory confirmed malaria cases among all OPD visits (disaggregated under 5 and over 5) | - | - | - |
| Prevalence of malaria parasitaemia (under 5 years) | - | 18 | - |

### Proportion of mothers who received two doses of preventive intermittent treatment for malaria during last pregnancy

This indicator is measured at household level and based on pregnant women aged 15 – 49 years who received at least two doses of IPTp during their last pregnancy that led to a live birth within the last two years out of a total number of surveyed women aged 15 – 49 years who delivered a live baby within the same period outlined above.  Pregnant women receive two doses of Sulfadoxine/Pyrimethemane (SP) during the second and third trimesters to protect from adverse effects of malaria in pregnancy and low birth weight; this can only be achieved if mothers complete the recommended two doses of IPTp. The target is to achieve 80% coverage by the end of 2013.  The progress however has remained low over the years from 22% in (TDHS 2004/5), 30% (THMIS 2007/8) to 27% (TDHS 2010), as shown in Figure 17 below.

Figure 17: IPTp coverage in recent household surveys

There is a need to carry out a comprehensive SWOT analysis for improvement of this indicator and benefit the intended target population, particularly in the light of the slight decline in coverage between 2007/08 and 2009/10.  Efforts will need to be tripled in order to reach the 2015 target.

### Proportion of vulnerable groups (pregnant women 15-49 years of age, children under 5 years) sleeping under an ITN previous night

This indicator is assessed at household level to measure progress made in increasing utilisation of Insecticide-Treated mosquito nets by pregnant women to protect them from mosquito bites and malaria infection. Assessment is based on the number of women aged 15 – 49 years who slept under an ITN the night preceding the survey out of total number of women aged 15 -49 years  who spend the previous night in a surveyed household. The target is to achieve 80% pregnant women use ITNs by 2013.  Reports from the household surveys show a steady increase in the use of ITNs by pregnant women from 16% (TDHS 2004/5), 26% (THMIS 2007/8) to 57% (TDHS 2010).

Likewise, use of ITNs by children under the age of five years is assessed in a similar manner and is based on the number of children under the age of five years who slept under an ITN the night preceding the survey out of all under five children who spend the previous night in surveyed household. Reports show a rapid increase in the children who use an ITN to prevent from malaria, ITN utilisation increased from 16% (2004/5 TDHS), 25% (THMIS 2007/8) to 64% (TDHS 2010), ie a fourfold increase over the period, as shown in Figure 18 below.

A further increase in the use of ITNs by these vulnerable groups is expected after completion of the Universal Coverage Campaign which is aimed at ensuring that everyone sleeps under a Long Lasting ITN.

Figure 18: Use of ITN for both Under-five and Pregnant Women

### Proportion of laboratory confirmed malaria cases among all OPD visits (disaggregated under 5 and over 5)

This indicator is defined as the number of microscopy or RDT confirmed malaria cases out of all cases <5, >5 seen at health facility and based on the data collected from 27 Sentinel Panel  of Districts (SPD) managed by the Ifakara Health Institute. No data are currently available for this indicator.

### Malaria parasite prevalence in children under five years of age

This impact indicator is measured at household level to determine the number of children with confirmed parasite in blood using either microscopy or RDT out of total number of children under five years old surveyed. It is useful in assessing the level of malaria transmission as we scale up effective interventions. The target is to reach 1% of children with malaria parasites by 2013. Only one national data point is available for this indicator; THMIS 2007/8, showed a prevalence of 18%.  An update for this indicator is expected in the planned THMIS 2011/12.

Figure 19 presents the wide variation in parasitaemia between regions.  It also shows that children in rural areas are three times more likely to have malaria parasites compared to their urban peers.

Figure 19: prevalence of malaria parasitaemia in Under-fives

### Tuberculosis and Leprosy

The Tanzania National Tuberculosis and Leprosy Program (TNLP) is one of the most successful TB programs in the world.  TB notification rates, treatment success and the proportion of leprosy cases diagnosed and successfully completed treatment have improved for the period of 2008 - 2009.

### Tuberculosis Notification rate per 100,000 population

In 2010, the notification rate of tuberculosis (all forms) is 147 cases per 100,000 populations. Similarly, notification rate of new smear positive tuberculosis cases is 57 cases per 100,000.  Figure 20 below shows the regional figures for 2010.  The graph also shows that there has been a slight fall in notification from 2008 to 2010.

Figure 20: Tuberculosis notification rate

### Percent of TB treatment success rate

The TB treatment success rate, is defined as the number of patients who successfully completed treatment as a proportion of the total tuberculosis cases diagnosed.  Analysis of the TB cohort notified in 2009 shows that the overall treatment success for new smear positive TB cases was 88%, This remained the same as in 2008 which was 88% (Figure 21). The program has surpassed the global target of 85% and the 2015 HSSPSIII target of 82%.  In addition, the majority of the regions have also surpassed the HSPSIII target. Now, the challenge is to maintain these high rates in future years.

Figure 21: TB treatment success rate by region, 2010

### Proportion of leprosy cases diagnosed and successfully completed treatment

Treatment outcome of PB leprosy cases notified in 2009 shows that 490 (92.6%) completed treatment. Among the 2,651 MB leprosy cases notified in 2008, treatment outcome results are available for 2,449 or 96% of the cohort. Of those notified, 2,518 (95%) completed their treatment successfully.

Figure 22: Leprosy treatment completion, 2009

### Incidence of cholera cases per 100,000 people

This indicator measures the number of cholera cases in a year as a proportion of the total population at risk. The incidence of cholera cases per 100,000 people was estimated to be 3,284 in 2005. At this time, there are no additional updates available. However, data reporting the number of cholera cases per region are available from the HMIS. The majority of cholera cases were reported in Mara (1349 cases), Mbeya (1256 cases), Mwanza (1042 cases) followed by Shinyanga (703 cases). Few cases were reported in the following regions:  Kagera (5), Iringa (3) and Tanga (1).

Proportion of treated cases of cholera that are deceased

This indicator measures the proportion of deceased patients who received cholera treatment. Out of the 7,115 cases identified in 2010, 135 of the treated cases died. The majority of deaths were reported in the following regions: Mwanza, Mbeya and Mara regions.

## Progress against indicators in the Performance Assessment Framework matrix

A sub-set of sector indicators are monitored under the Performance Assessment Framework (PAF) for General Budget Support.  The current baseline and targets for 2012 are shown in Table 4.

Table 4 PAF indicators for 2010/11

| Indicator | Baseline 2010 or 2011 | 2012 target |
| --- | --- | --- |
| Proportion of births at health facilities, national average | 54.8% (2010) | 60% |
| Proportion of districts in which at least 60% of births take place at a health facility | 54% (2010) | 55% |
| Persons with advanced HIV disease (CD4<200 or <350) currently receiving ARV combination treatment (disaggregated under 15 and over 15 and by sex) | 384,816 (2010) | 362,570 |
| Nurses and Nurse-midwives per 10,000 population | 3.96 (2010) | 4.0 |
| Total number of enrolment in health institutes | 6,713 (2011) (101%) | 7,474 (75%) |

# Chapter 3:  Summary of Progress against the Milestones agreed at Joint Annual Health Sector Review 2010

Tanzania Health SWAp Milestones 2010/2011 – Update

| Area | Milestone | Process Action Plan | Outputs/Indicators / Assumptions | Report/Update |
| --- | --- | --- | --- | --- |
| Various service delivery areas | 1. The National Essential Health Package reviewed and endorsed by July 2011. | Draft ToR for review of the NEHP by different TWGs according to their area and consolidate into one merged ToR by December 2010. Secure funding of the activity by January 2011 Carry out the review by representatives from LGAs, RHMTs, FBOs, CSOs, MoHSW, PMO-RALG, and DPs by March 2011 Finalized revision of NEHP by July 2011. | Indicator: National Essential Health Package finalized and approved Assumption: HSRS takes the lead in coordinating the process. | Draft National Essential Health Package available |
| District Health Services | 2. Linkages between the CCHP guidelines and HSSP III strategies in PlanRep, Epicor and other district-level systems finalized by July 2011. | Finalize CCHP Guideline by May 2011. Implement recommendations from consultancy report on integration of CCHP planning and reporting with PlanRep, Epicor and other District systems by December 2010. | Indicators: A: CCHP Guidelines finalized and approved B: CCHP planning and reporting integrated in PlanRep, Epicor and other District Administrative and Financial systems. | CCHP Guidelines finalized and approved CCHP Planning and reporting have been integrated into the PlanRep, however, not yet integrated in the Epicor Discussion are still under way between the UCC and other development partners such as the WAJIBIKA project |
| Hospital Reforms | 3. All Regional, District, and designated hospitals produce consistent annual operational plans and budgets by May 2011. | 1. Training material revised and improved by end of October 2010. 2. Thirteen (13) Hospitals that never developed a plan will receive three weeks training/coaching to prepare their plan, by March 2011 3. Eight (8) Regional Hospitals that developed a plan for last year will receive 5-day tailored coaching to improve their next plan, by January 2011 4. Guidance by RHMTs to hospitals which have not yet been trained in how to develop plans. | Process indicator 1: The training/coaching sessions take place in due time (13 hospitals) Process indicator 2: the tailored coaching take place in due time (8 hospitals) Process indicator 3: all hospitals submit their plan timely in the PMO-RALG planning schedule Process indicator 4: all submitted plans are evaluated against a grid. Main assumption: required funds are made available in due time. | The 3 training material (Planning, Management and quality improvement) were revised and improved by end of October 2010 The training/coaching sessions of 14 Regional Referral Hospitals took place in April 2011 (One Hospital - Ligula Hospital in Mtwara with self support through Regional funding-) The tailored coaching of 9 RRHs took place in 2011 Guidance by RHMTs to Council hospitals planning teams was conducted during preparation of the CCHP during preparation of the CCHP. |
| Health Financing | 4. Final Health Financing Strategy, its cost and action plan completed by May 2011. | 1. Inception Report discussed and work commence on 1st October 2010. 2. Consultative meetings to involve all stakeholders on the development of the Strategy 3. Completion of draft health financing strategy by February 2011. 4. Action plan for implementation of the strategy completed by May 2011 | Indicator 1: Inception Report completed. Indicator 2: All stakeholders involved in the development of the strategy Indicator 3: Financing Strategy and its cost completed Indicator 4: Action plan for the Strategy completed | Process Action Plan is revised and further detailed: The literature Review report was discussed and commenced in November 2010. Some Stakeholders were involved and there are initiatives to involve more stakeholders. Cost drivers study has been started and expected to be finalized by the end of the month. Some findings from this study will be included in the strategy paper, PER 2010 has been completed. Findings will be presented in the Technical Review Meeting. NHA has started and data analysis has already been done, the report is expected to be ready by the end of November. Costing study has also started; pilot phase was completed in Kilimanjaro region. The actual data collection will be in 4 regions more which includes Shinyanga, Mbeya, Dar Es Salaam and Iringa. This second phase will start at the end of October, 2011. Writing of the financing strategy has started, Health Financing Secretariat met with P4H advisor to brainstorm the structure and briefly content of the strategy. Six regions were visited to solicit comments from stakeholders at all levels from regions, district, health center and dispensaries. Both sectors public and private were involved. Next phase is to seek comments from central level. Also to create awareness at the higher decision making level both technocrats and political leaders. Financing Strategy will be completed by February 2012 and Action Plan by February 2012. CONCLUSION: The milestone is progressing well, but is expected to be fully achieved by February 2012. |
| PMO-RALG | 5. Health facility accounts established by June 2011. | MOHSW in collaboration with PMO-RALG to clarify with MOF on the establishment of health facility accounts | Assumption: Health Facility Accounts will be established with MOF and LGA as the main driving force. | PMO-RALG is still making follow-up with MOF on the issue of opening the facility accounts. |
| HRH / Social Welfare | 6. An increased number of health workers with the right skills ensured in the right locations by September 2011. | Revise national staffing guidelines for each level of care by March, 2011. Increase training capacity in both public and private health training institutions. Increase number of posted health workers, tracking of their reporting rates and retention 6 months after being posted. Increase proportion of skilled health workers from last year. Increase MTEF allocation for HRH at all levels for the year 2011/12 from the current level. | Indicator 1: Revised staffing guideline document completed by March 2011. Indicator 2: Number of new enrolled students compared to previous year increased by 850 by April 2011. Indicator 3: HRHIS report on number of posted health workers who are retained after 6 months after being posted. Indicator 4: HRHIS report on proportion of skilled health workers compared to unskilled health workers (presently Clinicians: 12.5%, Nurses 17.0% unskilled: 33.4%) | Staffing guidelines have been produced and draft is currently being validated. The final document will require harmonization with the proposed health package. Output indicator target has been surpassed. The number of pre-service enrolled students increased by 1348 in both Public and Private Training Institutions( 5365 in 2009/10 to 6713 in 2010/11) Number of posted health workers increased (from 4,090 to 5687) in 2009/10 to 2010/11). HRH Tracking study shows reporting rate of 63% and retention rate of 87% (2007/08 to 2009/10). Based on HRHIS reporting of 7628 HW (obtained from 4 Regions) a maximum of 24% can be categorized as unskilled. HRH Budget allocation as per Central MOHSW MTEF in 2010/11 and 2011/12 – See Table 5 at end of section. Main points include: Overall decrease of OC Development funds for District was difficult to obtain Overall increase in PE Devt. Funds for Central level for FY2001/12 comprise of GFR9 funds More funds are expected from CIDA and USG for Training Inst. Support. |
| PPP | 7. Revised PPP policy guidelines that are aligned to the National PPP policy, the corresponding PPP Act and other regulations produced; and a PPP tracking framework developed by August 2011. | Regarding PPP policy guidelines: 1A: Conduct desk review of the revised PPP policy guidelines to identify alignment issues in relation to the National PPP policy, the corresponding PPP Act and other regulations. 1B: Carry out meetings for PPP stakeholders at national, regional and district level for endorsement of the revised PPP policy guidelines 1C: Print and disseminate the revised guidelines Regarding PPP tracking framework: 2A: Undertake an inclusive assessment of the private health sector 2B: Develop a concept note defining monitoring and tracking needs for PPP and respective process and output indicators. 2C: PPP Office and NPPPSC adopting common tracking framework | Regarding policy guidelines: Indicator 1A: Desk study report by March 2011. Indicator 1B Reports of the meeting Indicator 1C: Revised guidelines disseminated to all regions and district by April 2011 Assumption for revision of policy guidelines: Timely funding of planned activities made available from multiple funding sources including from the private sector. Regarding PPP tracking framework Indicator 2A: Assessment Report available by August 2011. Indicator 2B: Concept Note available by April 2011. Indicator 2C PPP Tracking Framework report available by August 2011. Assumption for PPP tracking framework: Timely funding of planned activities made available from multiple funding sources including from the private sector. | 1.A Desk review of PPP Policy Guidelines conducted alignment done after the Act and Regulations were out 1.B One meeting was conducted another meeting scheduled on November 2011 1.C Printing not done 2. A Terms of Reference for Country Assessment developed funds and additional technical support secured. Preparatory meetings conducted. Process of hiring local ongoing. 2.B Tracking needs for PPP identified 2.C Draft common PPP tracking framework prepared |
| M&E/ HMIS | 8. In the framework of the “M&E strengthening Initiative 2010-2015”: at least four regions will produce a regional annual health sector performance profile report, including a summary of the HSSP III core indicator data available within the updated and rationalized HMIS. | M&E Strengthening Initiative year one operational plan approved by MOHSW and funding partners (November 2010) DHIS software installed in at least 5 regions (March 2011) Data entry completed or up to date for at least one DHIS module (June 2011) Regional staff complete extraction of data summary and produce report (August 2011) | Assumption: Finalization and timely agreement between MOHSW and funding partners on “M&E strengthening Initiative 2010-2015”. Initiative to officially start in November 2010! Indicator: At least four regions have produced and if requested are able to present at either the TRM/JAHSR 2011: A regional annual health sector performance profile report, including a summary of the HSSP III core indicator data available within the updated and rationalized HMIS | The M&E strengthening Initiative (MESI) was approved by end of 2010. DHIS software installed in 5 regions and 48 districts. (Lindi (6), Mtwara (6), Tabora (6), Shinyanga (8), and other districts included in Sentinel Panel of Districts. All districts completed data entry, and data validation. Data analysis and generation of core HSSP III indicators completed in two regions. (Mtwara and Lindi) Lindi presented summary of regional profile at M&E Focus Day. |
| Service Delivery MNCH | 9. Improve availability and supply for EmONC and child care at 80% of hospitals and health centres | Hire consultant to conduct assessment and develop distribution plan for EmONC equipment and health worker orientation plan by December 2010 Distribution of EmONC and paediatric equipment /Supplies done by June 2011 Delivery Pack procured and distributed to Dodoma and Coast region by June 2011 Walk in cold rooms procured and distributed and installed at National and Regional Vaccine stores by June 2011 400 Motor cycle Ambulances distributed by June 2011 | Distribution and orientation plan in place Equipment distributed Number of delivery procured and distributed Number of WICR distributed and installed at National and regional store Number of motorcycle ambulance distributed | Re 1: MUHAS/NIMRI hired just completed the assessment and submitted preliminary report, final report to be submitted in October 2011. Re 2: EmONC equipment delivered at MSD, supplied by (Anudha) and Sino – Africa, distribution to commence this October. EmONC procured with support from USAID were distributed to 23 health facilities in Pwani, Tabora and Dar es salaam Re 3: Funds sent to MSD, part packaging done and the Pack was launched during launch of CARMMA campaign (6/6/2011) Distribution to Pwani and Dodoma to begin 2nd week of October 2011 Re 4: 2 WICR for control Vaccine store procured with support from UNICEF and installed at MSD WICR for central vaccine store, under support of CIDA, received and stored at MSD, shelter secured awaiting installation. 26 WICR with standby generators, for regional Vaccine store, with support from CIDA received stored at MSD, awaiting for completion of shelters, generators still under clearance. 2 refrigerated trucks with support of CIDA, Purchase order issued awaiting shipment Refresher training program on cold chain management and maintenance (200 people for 5 days) with support from CIDA planned for 2012. Re 5. 45 motor cycle ambulances (21 from UNFPA) distributed, 130 registered to be distributed to all regions TOT of drivers done 84 being cleared Other consignment of 182 in process. |
| Service Delivery MNCH | 10. Strengthen capacity for Maternal, Newborn and Child Health care services 2011 | Finalize and print and distribute Focused Ante-Natal Care and Basic Emergency Obstetric and Newborn Care curricula by June 2011 Training and orient of National TOT June 2011 Revitalize and strengthen capacity of ICC | 1. Number of guidelines printed and distributed 2. Number of national TOT trained and oriented 3.1 TOR revised and endorsed 3.2 Three Inter-agency Coordinating Committee meetings conducted by June 2011 | Re 1: Family planning training curriculum printed 6,400 copies and in use Family planning basic training skills printed 3,050 copies and in use Contraceptive technology updates 3,100 printed and are is use Decision making in family planning 6,500 Focused Antenatal Care training manual 1500 printing progress Essential Newborn ……..Copies printed and are in use Basic Emergency Obstetric Newborn Care (BEmONC) training manuals 5,000 copies printed and are in use Re 2: First batch of 20 Trainer of Trainers in EmONC trained in October 2011 second batch to be trained in November 2011. Trainer of Trainers (TOT) in family planning 28 TOT trained Re 3: TOR for ICC revised and endorsed. Meetings held, attended by heads of agencies and last meeting chaired by PS. |
| Govern-ance & accoun-tability | 11. Further dissemination of new guidelines as well as rights and responsibilities of service users and boards implemented by June 2011. | Completion of CHSB guidelines by January 2011. Print and distribute revised guidelines to regional and district level facilities by April 2011. | Indicators: A: Revision of Guidelines completed B: Revised guidelines printed and distributed to Regional and District levels Assumption: The issue will be covered by TWG 1 | The CHSB guidelines have been revised and presented and shared by members of District and Regional TWG. The MoHSW in collaboration with GIZ are developing Swahili and English version leaflets on CHSB roles and responsibilities |
| Social Welfare | 12. The Social Welfare Strategic Plan finalized, and Regulations and guidelines related to Disability Act 2010 and The Law of the Child Act 2009 produced by June 2011. | Draft ToRs are ready by November 2010 for developing Strategic Plan that includes measures to align and bring together the SW Department with the rest of MoHSW translating Disability Act in Kiswahili and developing regulations for the Disability Act and the Law of the Child Act developing regulations for the Law of the Child Act Hiring a consultant November 2010 Dissemination of The Social Welfare Strategic Plan by April 2011. The plan will include measures to align and bring together the SW Department with the rest of MoHSW. Disability Act and its regulations by April 2011 The Law of the Child Act and its regulations and guidelines by May 2011 | Indicator No.1 Social Welfare Strategic Plan in place. Indicator No. 2 Translated Disability Act in Kiswahili. Indicator No. 3 Regulations for implementation of the Disability Act and the Law of the Child Act developed. | Draft ToRs for: Development of Social Welfare Strategic Plan awaits approval of the Social Welfare Policy by the Cabinet Secretariat The Persons with Disabilities Act 2010 regulations and Swahili version were developed and submitted to the State Attorney General Chambers for finalization and further actions Development of the Law of the Child Act (LCA) regulations Consultants were engaged for the task and 7 sets of regulations were developed and submitted to the State Attorney General Chambers for finalization The initial process of developing TORs for a consultant to prepare the Social Welfare Strategic Plan is underway Dissemination of: The Social Welfare Strategic Plan awaits approval of the Social Welfare Policy by the Cabinet Secretariat; hence it is not disseminated. Dissemination of the Disability Act is pending sanction by State Attorney General Chambers Dissemination of the Law of the Child Act is pending sanction by State Attorney General Chambers |
| NCD/NTD | 13. NCD and NTD implementation plans endorsed by the MoHSW Senior Management and the HR capacity of the MoHSW NCD and NTD sections strengthened by June 2011 | Draft ToR for developing implementation plans for NCD (November 2010) Request funding and engage consultant for NCD (December 2010) Submission of Implementation Plans to Senior Management for NCD (February 2011) Dissemination of implementation plans for NCD (March 2011) Appointment of 4 staff each to strengthen NCD and NTD sections Finalize NTD M&E framework and appropriate tools through support from a consultant by April 2011. | Indicator: 1) NCD Implementation Plans in place 2) NCD and NTD sections established with adequate staff. 3) M&E framework and appropriate tools for NTDs in place and functional Assumptions: Timely funds for engaging consultant. Allocation of staff | NCD Action plan 2011-2015 is completed and first year activities are included in the MTEF 2011/21 Action plan is yet to be disseminated. Will be disseminated electronically 2 out 4 staff required have been allocated to NCD. Waiting for management to allocate the rest. M&E framework is included as part of the Action Plan NTD NTD strategic plan was completed and endorsed in 2010. the Plan is being revised to comply with WHO guidelines M&E framework for NTD is not completed but tools are ready (recording and reporting tools) Proposal of staffing for NTD submitted to management approval |
| Pharma- ceutical | 14. Agreement between MOHSW, PMO-RALG and MSD for performance of each party’s responsibilities in the provision of medicines and medical supplies in place by September 2011. | 1. Implement equitable resource allocation plan (January 2011) 2. Establish mechanism for timely and predictable disbursement of funds to MSD facility accounts 3. Benchmark MSD order fulfilment rates for the essential health package items by level of care, lead times for ordering and delivery up to facility. 4. Develop sentinel monitoring system and incorporate indicators and reporting within district health information system (June 2011) 5. Incorporate agreed performance standards in the operating procedures at MSD, MoHSW, PMO-RALG and Councils (June 2011) | Output: Agreement in place Indicators; Funds allocated and timely released Benchmarks and sentinel monitoring indicators available Important assumptions: Basket and Government funds for medicines are pooled to support systematic allocation plan, and disbursed to MSD on time. Fast tracking of medicines and logistics indicators within the HIMS roll-out. Timeline for incorporation of performance standards depends on individual institution | New allocation formula for PHC for all levels; implementation started Jan 2011. So far two disbursements have been done with new formula. The formula has two stages. Stage 1: Allocating fund per council based on the council population, poverty and under-5 mortality. This stage is fully implemented with the new formula. Stage 2: Allocation of funds based on the services population per health facility. This stage is not fully implemented; so far only 39 (30%) councils have submitted the service population per facility. Mechanism for timely and predictable disbursement of funds to MSD facility accounts to be finalized and approved for implementation this financial year. Benchmarks and targets will be set based on monitoring and reports of MSD order fulfilment from new ERP at MSD and electronic logistics management information systems (DHIS and ILS Gateway) Ifakara Health Institute is contracted to pilot tracer and logistics indicators for DHIS in sentinel panel of districts, and incorporates in HMIS roll-out. IHI started with 5 councils, (Bagamoyo, Rufiji, Kinondoni, Temeke, Ilala) results expected to start flowing from October 2011. Incorporation of performance standards in operating procedures is pending the completed development of ERP at MSD. |
| Nutrition | 15. Nutrition posts established at Regional Secretariats and, a budget for the placement of nutrition personnel, as per approved staffing, allocated by 25% of councils by August 2011. | 1. Using Essential Nutrition Package, sensitize Regional Secretariats on the need to establish nutrition posts at Regional level and Councils on the need to fill vacant nutrition posts by August 2011. 2. Develop detailed job descriptions and a training programme for nutritionists by August 2011. 3. Develop tools to plan, budget and implement nutrition services at district/regional levels by August 2011. | Process Indicator 1a: 500 copies of Essential Nutrition Package printed and disseminated. Process Indicator 1b: Sensitisation meetings with 23 Regional Secretariats and representatives of all Councils. Process Indicator 3: Job descriptions and training programmes developed and disseminated. Process Indicator 4: Availability of nutrition planning, budgeting and implementation tools. Output Indicator 1: Regional Secretariat Organogram includes Nutrition posts. Output Indicator 2: 25% of district councils allocate budget for nutrition. Assumptions: Sensitisation and awareness creation will result in action i.e. Secretariats/Councils taking up recommendations. | 1. Essential Nutrition Packaged distributed to all Councils and Sensitization of Regional Secretariats on the need to establish nutrition posts at Regional level and Council is ongoing. 14 Region have been covered by mid October 2011 2. Job description for Nutrition Officers at Regional District and Word levels are in peace and framework of training programme for district nutritionists developed. 3. Tools to plan budget and implement nutrition services at district/regional level not done. Included in process Action Plan in 2012/2013 Milestone. |

Table 5 HRH budget allocation

From Milestone no 6.

|  | FY 2010/11 | FY 2011/12 |
| --- | --- | --- |
|  | Central | District | Central | District |
| OC. | 13,763,242,425 | 32,881,353,000 | 13,231,531,200 | 32,331,353,000 |
| Dev. | 4,971,570,000 |  | 10,877,231,360 |  |
| PE | 8,023,931,525 | 209,118,777,000 | 9,252,647,200 | 244,949,652,000 |
| Total | 26,758,743,950 | 242,000,130,000 | 23,584,178,400 | 277,281,005,000 |

# Chapter 4: MTEF Implementation performance 2010/11

MTEF Implementation Status

Using the information from the MoHSW (Vote 52) Annual Implementation Report for the FY 2010/11 we present the MoHSW budget and expenditure by Departments. Table 6 below shows the implementation status in terms of budget execution.

Table 6 MTEF implementation status (Recurrent) in 2010/11

| Sub Vote | Description | Budget | Actual Expenditure | Variance | Exp. as % of Budget 2010/11 |
| --- | --- | --- | --- | --- | --- |
| 1001 | Administration and General | 4,772,188,004 | 3,389,654,377 | 1,382,533,627 | 71.0 |
| 1002 | Finance and Accounts | 704,590,000 | 668,132,279 | 36,457,721 | 94.8 |
| 1003 | Policy and Planning | 884,507,760 | 525,243,440 | 359,264,320 | 59.4 |
| 1004 | Internal Audit Unit | 91,850,000 | 31,539,282 | 60,310,718 | 34.3 |
| 1005 | Information Education and Communication | 268,175,470 | 147,395,788 | 120,779,682 | 55.0 |
| 1006 | Procurement Management Unit | 236,342,000 | 161,811,512 | 74,530,488 | 68.5 |
| 1007 | Legal Services Unit | 82,200,000 | 46,453,446 | 35,746,554 | 56.5 |
| 2001 | Curative Services | 159,486,499,336 | 154,703,576,179 | 4,782,923,157 | 97.0 |
| 2003 | Chief Medical Officer | 8,877,971,890 | 6,466,909,388 | 2,411,062,502 | 72.8 |
| 3001 | Preventive Services | 28,896,218,252 | 22,731,145,079 | 6,165,073,173 | 78.7 |
| 4002 | Social Welfare | 3,891,251,338 | 3,536,414,727 | 354,836,611 | 90.9 |
| 5001 | Human Resource Development | 21,787,173,950 | 18,913,889,187 | 2,873,284,763 | 86.8 |
|  | TOTAL | 229,978,968,000 | 211,322,164,685 | 18,656,803,315 | 91.9 |
| Development | 448,442,515,000 | 243,352,015,897 | 204,511,154,232 | 54 |

# Chapter 5: Council health performance

The MOHSW in collaboration with PMO-RALG is responsible for assessing and preparing the consolidated summary analysis of the Comprehensive Council Health Plans (CCHP) and progress reports. The analysis aims to provide information for the management of MOHSW and PMORALG for decision-making towards ensuring that quality health services are delivered at the LGAs level. In addition, the report is presented to the Health Basket Financing Committee for approving the Health Basket Fund for the implementation of the annual LGAs health plans (ie the CCHPs) and supportive supervision plans of the Regional Secretariat/RHMT, MOHSW and PMORALG.

This chapter is based on the Summary and Analysis of Comprehensive Council Health Plans FY 2011/12 and focuses on Council and Regional capacities for budgeting and planning, their compliance with national guidelines as well as existing capacities for the implementation of activities in the first part. The last part reports actual Council performance in key areas from CCHP samples.

### Planning and budgeting capacities

CCHPs from a total of 132 councils from Tanzania mainland were assessed, of which 126 (95%) councils were recommended for funding while six (5%) councils were not recommended (Namtumbo DC, Liwale DC, Kilolo DC, Arusha MC, Mufindi DC and Siha DC). Though this is an improvement when compared to the previous year where 19 councils were not recommended for funding, there is still need to assist selected councils to improve their planning and budgeting capacities. When assessing CCHP FY 2011/12 performance by region, Ruvuma region performed below the minimum pass point (70).

Figure 23: CCHP 2011/12 performance per region

The review indicated that among 132 councils about 93 (70.5%) had included health centre and dispensary plans in the CCHP.  The majority (79.5%) of the councils were found to have involved both FBOs and NGOs in the council planning team.   While theoretically the majority of members of planning team for CCHP are supposed to be members of the CHMTs, who are supposed to have substantive positions and not acting position, the assessment revealed that only 41.7% of the councils had members with substantive positions in planning team. In comparing this result with that of status performance of the councils (CCHP scores), there is a statistically significant relationship between the two data, whereby most of those councils not recommended have either most or some of its planning team members were in the acting position and not in substantive posts.

In addition, some councils have problems formulating targets in a meaningful way and linking planned activities with identified problems. Some councils also failed to correctly interpret the new CCHP guidelines, specifically how to incorporate basic information into the executive summary.

Computer skills were also noted to be a challenge in most of the councils, particularly in the application of PlanRep software, formatting and spreadsheet calculations as well as editing Council and RHMT plans prior to submission to the central level. It was further observed that the PlanRep tool was only used by 55 (41.7%) of the Councils. Some of the councils stated that they used Microsoft Excel after realizing some shortfall in the revised PlanRep tool, such as the cost-sharing budget not appearing in the printouts or receipts in kind from MSD not being reflected in the main budget summary.

Shortfalls in planning and budgeting included failure of some districts to allocate sources of funding targeted for IMCI, STI syndromic management, integrated management for emergency and essential surgical care, case management and prevention for acute febrile illnesses activities, Social Welfare, health promotion interventions and emergency preparedness activities.

### Budget allocated for delivery kits

Delivery can be made safer by preventing infection through the use of a clean delivery kit, and these items are therefore considered to contribute to reduction of maternal and child mortality.  In Tanzania, as in many developing countries, most births in rural areas take place at home without medical assistance.

In FY 2010/11 and FY 2011/12, the Tanzania Government through MOHSW has been taking positive actions to ensure that delivery kits are available and provided free in all health facilities. However, the budgets for delivery kits differ from council to council depending on the needs and availability of last financial year’s stock. While 77.3% of councils budgeted for delivery kits in FY 2010/11, this decreased to 55.3% in FY 2011/12. The councils which budgeted a reasonable amount compared to others were, Mbulu DC (Tshs 32.8m), Muleba DC (Tshs 20.2m) and Mtwara DC (Tshs 20.0m).  Other councils had either budgeted below TShs 20.0m or not budgeted for this item at all.

When combining both financial years’ budgets for delivery kits, further analysis indicate that Coast, Dar es Salaam and Arusha regions had very low budget (below Tshs 20.0m for the combined years), while in Shinyanga, Manyara, Morogoro and Iringa regions their total budget was above TShs 100m. These latter regions can be considered to have allocated a reasonable amount for delivery kits in both years.

Figure 24: Allocation of Delivery Kits per regions

### Activities budgeted for Council Health Service Boards and other Health committees

In FY 2011/12, all councils except Nkasi DC allocated a budget for Council Health Services Boards (CHSB) and Health Facility Governing Committees (HFGC) activities to facilitate operation and functioning of these organs that are supervising and coordinating health services at the Council level as directed in the CHSB guidelines. 98% of Councils budgeted below TSh 50m (except Kinondoni MC and Iringa DC).

### Budget allocated to priority areas and summary of all sources of funds

Many areas need to be funded through CCHP activities and programmes.  However, due to funding constraints, there is a need to prioritise. In the CCHP activities for FY 2011/2012, eleven priority areas were identified.  These were:

- Maternal  newborn and child health

- Communicable disease control

- Non-communicable diseases

- Treatment and care of common disease of local priority

- Environmental health and sanitation

- Strengthening  social welfare and  social protection services

- Strengthening Human Resources for Health and capacity

- Strengthening the organization structure and institutional management at all levels

- Emergency Preparedness and Response (EPR)

- Health promotion

- Traditional medicine and alternative healing

Most funds were allocated to the priority areas of strengthening human resource for health and capacity and strengthening organization structure and institutional management at all levels. These two areas had absorbed more than two-third (73%) of total funding. On the other hand, EPR and health promotion were each allocated less than 1% of total funding.

Figure 25: Total amount allocated to each Priority Area

Figure 26 shows the distribution of the total CCHP budget allocations by region.

Figure 26: Percent of total budget allocated in the CCHP by region

Top 10 Councils that could allocated more than Tsh 10 billion each were Kinondoni MC, Temeke, Kahama Dc, Ilala MC, Myomero DC, Arusha MC and

Regions such as Singida, Rukwa, Ruvuma, Lindi, Mtwara, Manyara, Mara, and Kigoma, which are well known as peripheral regions, disadvantaged with distance and poor infrastructure, received a lower allocation (3% each) compared to other regions.  The role of the human resource crisis in this scenario must be explored.

At council level, the highest health fund allocations were made to Kinondoni MC, Temeke MC, Kahama DC, Ilala MC, Myomero DC, Arusha MC and Mbozi DC. The 10 Councils with health fund allocations of less that TSh 1 bn were Ileje DC, Rorya DC, Lindi MC, Mkinga DC, Mpanda TC as well as Siha DC.

Table 7 Top and Bottom 10 of Health Fund Allocations by Councils

The main source of CCHP Funding is the Block Grant (BG) (52%). This includes Personal Emoluments (PE) and Other Charges (OC), though it is further observed that 88% of Block Grant Fund is mainly used for paying salaries (PE) and other employee benefits or allowances.

Figure 27: CCHP Funding Sources in Percent

### Health Facility status

Health facilities include hospitals, health centres and dispensaries. District designated Hospitals (DDH) complement the Government district hospitals for those council where there is no government hospital. These are the places where health workers provide health services to the community. Other units or centres which provide health services comprise of mobile services, first aid, local healers, the upcoming Accredited Drug Dispensing Outlets, Duka la Dawa Baridi etc.

Figure 28: Percent of health facilities by type in Tanzania Mainland 2010/11

The total number of health facilities was 6,150 as per this assessment. Among these seventy five percent (75.5%) are owned by Government, while FBO/volunteers contribute 12.5% of health facilities.

The health facilities ownership ratios between Government and other health facilities owner were 60:40 before 2008/09 and shifted to 75:25 by 2011/12. The increase is visible in number of dispensaries whereby it has risen from 4,878 to 5,332 dispensaries, an increase of 454 dispensaries in three years, most of which has been built by government (99%) and very insignificant increased number of health facilities by the other stakeholders such as FBO, parastatal and private company or individual. These might be due to the MMAM programme whereby there should be a dispensary in every eligible village by a given period.

Table 8 Number of health Facilities by type and ownership in Mainland Tanzania by June 2011

|  | Govt. | DDH | FBO/VA | Parastatals | Private | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Hospital | 99 | 17 | 77 | 11 | 36 | 240 |
| Health Centers | 417 | 1 | 103 | 13 | 44 | 578 |
| Dispensaries | 4127 | 0 | 590 | 117 | 498 | 5332 |
| Grand Total | 4643 | 18 | 770 | 141 | 578 | 6150 |
| Percent | 75.5% | 0.3% | 12.5% | 2.3% | 9.4% |  |

### Human Resources per LGA

The review also looked at the number of staff in each LGA, by cadre.  The assessment revealed that there is serious shortage of both number and qualified health workers of different cadres in most of the councils. The study has indicated that, in particular, the available number of Specialist Doctors, social welfare officers, and ADO were below the half of the requirement according to the establishment, while Cadres such  as nurse/nurse midwives/public health nurse II, Clinical Officers, health officers, pharmacist/pharmacy technician and radiographer have increased slightly (to above 50%, but still below 60%). In the similar assessment carried out in year 2009, these categories were lying below 50% of the establishment and hence were the cadres with greatest shortage.

Figure 29: Human Resources per LGA, 2010/11 – as per Establishment

The regions with highest shortages of health workers were Lindi (77.5%), Rukwa (70.8%), Kigoma (70.4%), Ruvuma (64.4%), and Mara (61.8%). Other regions facing the similar risk, whose inadequacy is above the half of required staff were Tabora (60.8%), Mtwara (60.2%), Mbeya (59.7%), Singida (56.7%), Manyara (56.2%), Iringa (56.1%) and Dodoma (55.5%).  As might be expected, Dar es Salaam region shows the lowest deficit, at slightly over 20%.

This assessment has clearly indicated that the majority of health workers are clustered in those regions with big cities and towns, such as Dar Es Salaam, Mwanza, Kilimanjaro and Arusha.

Figure 30: Human resource deficit in each region by June 2010 (all cadres combined)

### Council performance for selected indicators

The following part is showing trends in council performance for selected health indicators. These indicator values differ from those reported in chapter 2 of this report as they come from a different source, the CCHPs rather than surveys, and are reported for a different period.  In addition, only a sample of the 132 Councils recognized by CCHP in Tanzania Mainland was chosen, influencing the analysis results. However, it is important to observe trends in council performance in order to take action where trends go to an unintended direction.

Tuberculosis Performance

In the TB performance assessment, a sample of about 120 councils was employed. The total number of TB cases regarding this sample size was 52,587. Current data (2010) has indicated that; there were large number of cases in Dar es Salaam city compared to other areas, Kinondoni MC (4,423), Temeke MC (3,886) and Ilala MC (2,368). Other councils with high TB cases were Geita DC (1,078), Mbulu DC (1,070) and Arusha MC (1,052). Furthermore, in this sample, councils with fewer TB cases were Morogoro MC (12.5), Pangani DC (56) and Hai DC (69).

Figure 31: Trend of TB cases in 2008, 2009 and 2010

The TB treatment completion rate has moderately increased from 83.2% in 2008 to 89.2% in 2010. The finding has further revealed that, the TB success cure rate (patients cured who were smear positive - 6 or 8 months after starting treatment) has increased by 4.5%.

HIV/AIDS and PMTCT/VCT

A sample of 110 councils has indicated that there were 631,263 HIV cases in 2010. The councils with high cases compared to others in this particular sample were Kinondoni, Ilala, Mbeya, Mufindi, Tabora and Mbeya while Ileje, Ngorongoro and Ileje were identified as councils with fewer HIV cases according to this sample.  Furthermore, the three year trend suggests that the cases might have increased from year 2009 to 2010 assuming that the sample is representing the whole population.

The importance of ARVs was also measured during the assessment for a sample of 109 councils.  Ilala MC had the highest number of HIV patients on ARVs (51,066) than any other council by June 2010. Other councils with large numbers of ARV patients were Kinondoni MC (40,122), Temeke MC (27,633), Mbeya MC (13, 489) and Mufindi DC.

The trend of HIV patients on ARVs has shown that, the number has been constantly increasing from 2008 to 2010.

Figure 32: Trend of HIV cases and patients on ARVs

The trend in PMTCT and Voluntary Counselling and Testing (VCT) in four consecutive years indicates that there has been a decrease since 2007. It is suspected that this decline is due to stigma, which remains a barrier to seeking VCT despite opening more VCT sites.

Figure 33: Trend of PMTCT and VCT

Maternal Health

Assessment of a sample of 100 of the currently existing 132 councils indicated that the estimated percentage of birth attendance at health facility was 66.7%.  Councils reporting low (1% or below) home deliveries were Babati TC (0), Morogoro MC (0.6%), Songea DC and Songea MC each 1%.

On the other hand, 13% of councils report more than 50% of births being delivered at home or elsewhere than recognized health facilities. The community delivery is highest in Kinodoni MC (87%), Kiteto DC (75%) and Hanang DC (70%).

Figure 34: Trend of births attendance at health facility and community delivery since year 2008

Analysis from a sample of 124 councils has indicated that 21% of councils had ANC attendance rate of 100 percent or above by June 2010.  Mbeya CC and Iringa MC had the highest rates, at 166% and 156% respectively, whereas 2% of the councils have attendance rate below 50 percent, namely Nkasi DC (30%), Urambo DC (35%) and Mwanza CC (48%).

Figure 35: Trend in Antenatal Care attendance rate since year 2007

Malnutrition

Malnutrition results from imbalance between the body's needs and the intake of nutrients, which occurs when a person's body is not getting enough nutrients (undernutrition) or getting excess nutrients (overnutrition).

This assessment has confirmed that severe malnutrition rate was high in Dar es Salaam, Mara, Lindi, Dodoma and Arusha regions in 2010 while in Coast, Singida Ruvuma, Tanga, Kagera, Kilimanjaro, Rukwa, and Mwanza regions the malnutrition is less than 1%.

Figure 36 Severe malnutrition rates from CCHP assessment

Furthermore, the CCHP assessment has indicated that, the proportion of low birth weight were much higher (15%) in Dar es Salaam region while it is lower (below 2%) in Kigoma, Mara and Kagera regions.

# Chapter 6: Health system indicators, including health financing and expenditure

The HSSP III indicators on health financing and spending are largely drawn from the Public Expenditure Review.  Due to timing constraints, these indicators tend to lag behind service delivery indicators, and therefore indicators of actual expenditure tend to reflect the previous financial year, ie FY2009/10.   This is an area where further efforts are required to provide at least provisional data for the year under review.

## Basic Expenditure Performance Indicators for the Public Health Sector in Tanzania

### 6.1.1	Per capita Health Spending at Central Level

Per capita budget allocation on health increased from US$ 10.71 in 2006/07 to US$ 18.80 in 2010/11. Nominal per capita spending on the public health sector increased from TZS 13,375 in 2006/07 to 21,716 in 2010/11. This represents an increase by more than seventy five percent. Table 9 below shows the nominal and real per capita public health expenditures. Per capita expenditures on health increased from TZS 11,298 (US$ 9.5) in 2005/06 to an estimated TZS 21,327 (US$ 14.7) in 2009/10. In real terms, the per capita public health expenditures increased from about US$7 in 2005/06 to US$ 9.62 in 2009/10. The estimate for 2010/11 is US$ 10.55.

Table 9: Per capita expenditure performance indicators for the public health sector

|  | 2005/06 | 2006/07 | 2007/08 | 2008/09 | 2009/10 | 2010/11 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Actual Exp | Approved Estimates | Actual Exp | Approved Estimates | Actual Exp | Approved estimates | Actual Exp | Approved estimates | Actual Exp | Estimates |
| NOMINAL (TZS) | 11,298 | 13,379 | 13,224 | 15,374 | 14,251 | 17,771 | 17,118 | 21,726 | 21,327 | 27,254 |
| REAL (TZS) | 8,308 | 9,163 | 9,058 | 10,115 | 9,376 | 11,392 | 10,973 | 13,009 | 12,770 | 15,485 |
| NOMINAL USD | 9.49 | 10.71 | 10.58 | 12.18 | 11.29 | 13.46 | 12.96 | 15.00 | 14.71 | 18.80 |
| REAL USD | 6.97 | 7.34 | 7.25 | 8.01 | 7.43 | 8.63 | 8.31 | 9.80 | 9.62 | 10.55 |
| Deflator | 1.36 | 1.46 | 1.46 | 1.52 | 1.52 | 1.56 | 1.56 | 1.67 | 1.67 | 1.76 |
| Exchange Rate | 1,192 | 1,249 | 1,249 | 1,262 | 1,262 | 1,320 | 1,320 | 1,327 | 1,327 | 1,468 |
| Population (millions) | 37.7 |  | 38.9 |  | 40.1 |  | 41.3 |  | 42.6 | 43.8 |

### Local Government Health Spending

It is important to note that data collected at the central level underreported the expenditures at the LGAs level.  According to the information collected from MoF, LGAs spent a total of TZS 256 billion on health services in 2009/10 compared to TZS 309 billion reported at LGA level by the 120 LGAs. The difference is significant, and if all 133 LGAs were included, it could continue to increase. This could be echoing the issue of “timeliness” of reporting to MoF by LGAs. In this case, it may be assumed that some funds released at the end of the last quarter have not yet been reported and the amount which LGAs report to the MoF at the end of the year is less than what is reported later. Other scenarios could include LGAs not fully reporting the financing from other sources. Out of this TZS 166 billion, 65% was spent on recurrent expenditures with 75% being utilized for personnel emoluments. The Government contributed 68% of funds spent at the LGAs level in 2009/10. The development expenditures were financed by Development Partners mainly through basket funds (59%).

Table 10: Local Government health spending

|  | 2009/10 | 2010/11 |
| --- | --- | --- |
|  | Approved Estimates | Actual Expenditure | % of Total (Actual) | Approved Estimates |
| RECURRENT |
| Government Fund | PE | 147,365,845,071 | 124,783,990,405 | 75% | 177,942,095,886 |
|  | OC | 54,302,436,606 | 41,351,987,182 | 25% | 39,905,098,603 |
| Total Recurrent | 201,668,281,676.63 | 166,135,977,587.21 | 65% | 217,847,194,489 |
| DEVELOPMENT |
| Government Fund | 10,318,112,901 | 8,481,372,209 | 9% | 11,948,713,335 |
| Donor basket Fund | 59,800,245,304 | 53,022,345,088 | 59% | 53,610,202,818 |
| UNICEF | 1,029,740,696 | 905,457,726 | 1% | 1,801,155,000 |
| Global Fund | 3,855,410,242 | 3,185,018,340 | 4% | 6,815,244,752 |
| Others | 32,659,917,553 | 21,484,083,550 | 24% | 61,944,237,643 |
| Complementary Financing | 4,263,911,319 | 2,361,378,669 | 3% | 3,620,965,481 |
| Total Development | 111,927,338,014 | 89,439,655,582 | 35% | 139,740,519,028 |
| Total Budget | 313,595,619,691 | 255,575,633,169 |  | 357,587,713,517 |

### Health Sector Financing Indicators

The proportion of the national budget (including CFS) going to the health sector in 11.8% was 2006/07 and in the estimate for 2010/11 was 10.3%.  However, excluding consolidated fund services, the proportion fall from 13.3% to just 12.1 % which is a marginal decrease over the period.

Table 11: Selected health sector financing indicators in USD

|  | Indicator | Baseline (2006/07) | FY 08 | FY 09 | FY 10 | FY 11 |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Budget | Actual | Budget | Actual | Budget | Actual | Budget |
| 1(a) | Proportion of National Budget on Health (including CFS) | 11.8% | 10.3% | 11% | 10.4% | 10.7% | 9.7% | 9.8% | 10.3% |
| 1(b) | Proportion of National Budget on Health (excluding CFS) | 13.3% | 11.3% | 12.2% | 11.5% | 12% | 11.6% | 12.9% | 12.1% |
| 2(a) | Total public health sector spending (TZS, Mn) | 514 | 616 | 571 | 764 | 701 | 925 | 908 | 1,193 |
| 2(b) | Total government health spending (TZS, Mn) | 348,890 | 413,258 | 378,113 | 459,496 | 461,504 | 548,658 | 578,682 | 643,011 |
| 2(c) | Total donor health spending (TZS, Mn) | 164,715 | 202,490 | 192,959 | 304,098 | 239,569 | 376,441 | 328,845 | 549,712 |
| 3(a) | Nominal per capita health spending (TZS) | 13,224 | 15,374 | 14,251 | 17,771 | 17,118 | 21,726 | 21,327 | 27,254 |
| 3(b) | Real per capita health spending (TZS) | 9,058 | 10,115 | 9,376 | 11,392 | 10,973 | 13,009 | 12,770 | 15,485 |
| Shares of public allocation to health (Central, Regional and Districts) |
| 4(a) | Central | 57% | 51% | 49% | 52% | 51% | 46% | 43% | 41% |
| 4(b) | Regional | 7% | 10% | 10% | 10% | 10% | 10% | 9% | 10% |
| 4(c) | District | 36% | 39% | 41% | 38% | 39% | 44% | 48% | 48% |

### Trends in Health Sector Spending

In line with the projection of the MTEF Budget Guidelines, expenditure in the public health sector increased following increased programmatic efforts to combat Malaria, TB, Reproductive and Child Health and HIV and AIDS. The budget guidelines focus on Prevention and treatment of Malaria; Rehabilitation and rationalization of regional hospitals; Scaling up of provision of immunization services and other Reproductive and Child Health services; Scaling-up of proven non-Anti-Retro Viral (ARV) interventions, including Tuberculosis (TB) prevention and treatment of opportunistic infection in People Living with HIV and AIDS (PLWAs); Facilitating equitable, sustainable and cost effective access to ARV for all affected households with emphasis on ARV education; and Improving human resource capacity at all levels in terms of quality, skills mix and quantity.

The public health sector has two main sources of resources: domestic or internal and external resources. External resources are channeled to the health sector in three forms: the general budget support, health basket funding, and direct programme or project support. As complements to the sources of finance for the health sector, there exist the National Health Insurance Fund (NHIF) and community contributions in the form of prepayment schemes and direct fees in service delivery points. However, evidence over time shows that though important at the service delivery point, complementary financing in Tanzania is just a marginal proportion of the total public health sector financing. Apart from the subventions received from the central government, councils generate their incomes from various local sources and set aside some funds for the health sector.

## Expenditure Trends: Recurrent Vs Development from 2005/06 – 2010/11

The recurrent actual expenditures has increased from TZS 308,045 million in 2005/06 to TZS 532,742 million in 2009/10, while development expenditures increased from TZS 118,329 million to  TZS 374,785 million during the same. The share of the development budget to the total continues to improve from 28% in 2005/06 to 41% in 2009/10. It is worth noting that in 2009/10/11, the development budget is receiving more allocation than the recurrent budget. This is a result of new funding mechanisms, such as the Global Fund, which are budgeted under the development vote. It is important to note that although Global Fund is budgeted under the development vote, there is significant recurrent expenditure within that Fund. Quantification of the recurrent and development components of the Global Fund is beyond the scope of the PER from which these data are drawn.

Table 12: Expenditure Trends: Development Vs Recurrent (TZS billion)

|  | 2005/06 | 2006/07 | 2007/08 | 2008/09 | 2009/10 | 2010/11 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Actual Exp | Approved Estimates | Actual Exp | Approved Estimates | Actual Exp | Approved Estimates | Actual Exp | Approved Estimates | Actual Exp | Estimates |
| Total rec-urrent | 308.05 | 397.64 | 391.79 | 394.89 | 360.29 | 402.38 | 428.56 | 498.61 | 532.74 | 578.61 |
| Total develop-ment | 118.33 | 122.23 | 121.81 | 220.85 | 210.78 | 361.21 | 272.52 | 426.49 | 374.79 | 614.11 |
| Total on Budget | 426.37 | 519.87 | 513.61 | 615.75 | 571.07 | 763.59 | 701.07 | 925.10 | 907.53 | 1,192.72 |
| Rec as a % of Total | 72% | 76% | 76% | 64% | 63% | 55% | 61% | 54% | 59% | 49% |
| Dev as a % of Total | 28% | 24% | 24% | 36% | 37% | 45% | 39% | 46% | 41% | 51% |

### Government Spending on the Health Sector

The share of public spending on health to total government expenditure as a percent of Total Government Expenditure (TGE), including CFS, oscillated between 12% and 10% between 2005/06 and 2009/10. However the share of public spending on health to total government expenditure (excluding CFS) increased marginally from 12.1% in 2008/09 to 12.9% in 2009/10. The level of public spending would be relatively low if the donor funds, which account for about 34% of public health spending, are netted out. Although GoT committed itself to increasing the health allocation budget to 15% of total government allocation in line with the Abuja declaration, expenditure figures for the last five financial years indicate that this is far from being realized (see Table 13).

In absolute terms, expenditures by public sector on health have more than doubled from TZS 426 billion in 2005/06 to TZS 908 billion in 2009/10. The public health expenditures as a percentage of GDP increased from 2.7% in 2005/06 to 3.2% in 2009/10.

The table below shows the trends in share of health budget and expenditure in total government budget and expenditure (2005/06 – 2009/10).

Table 13: Trend of total public spending on health (Billion TZS)

| DESCRIPTION | 2005/06 | 2006/07 | 2007/08 | 2008/09 | 2009/10 | 2010/11 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Actual Exp | Approved Estimates | Actual Exp | Approved Estimates | Actual Exp | Approved Estimates | Actual Exp | Approved Estimates | Actual Exp | Estimates |
| Total Public Spending Excluding CFS | 3,018 | 4,496 | 3,862 | 5,452 | 4,685 | 6,631 | 5,847 | 7,994 | 7,029 | 9,891 |
| Total Public Spending Including CFS | 3,578 | 4,972 | 4,338 | 5,998 | 5,209 | 7,320 | 6,536 | 9,517 | 9,239 | 11,609 |
| Total public Health Spending | 426 | 520 | 514 | 616 | 571 | 764 | 701 | 925 | 908 | 1,193 |
| Health as % of Total Expenditure excluding CFS | 14.1 | 11.6 | 13.3 | 11.3 | 12.2 | 11.5 | 12.0 | 11.6 | 12.9 | 12.1 |
| Health as % of Total Expenditure including CFS | 11.9 | 10.5 | 11.8 | 10.3 | 11.0 | 10.4 | 10.7 | 9.7 | 9.8 | 10.3 |
| Health as % of Total Expenditure including CFS | 11.9 | 10.5 | 11.8 | 10.3 | 11.0 | 10.4 | 10.7 | 9.7 | 9.8 | 10.3 |
| GDP (current Price) | 15,966 |  | 17,951 |  | 20,948 |  | 24,782 |  | 28,213 | 30,188 |
| Total public Health Expenditure as Percentage of GDP | 2.67 |  | 2.86 |  | 2.73 |  | 2.83 |  | 3.22 | 3.95 |

## Public Health Expenditure by Financing Sources

The public health sector continues to be financed primarily by two sources, the Government and the Development partners. These are shown in Table 14 below.  Expenditures from government funds nearly doubled from TZS 296,819 million in 2005/06 to TZS 578,682 million in 2009/10. Foreign funds increased by 154% from TZS 129,555 million in 2005/06 to TZS 328,845 in 2009/10. The huge increase in non-basket funding is due to additional money from the same development partners. The Global Fund contributed significantly to this increase. GoT remained the main source of health financing contributing more than two-thirds of all expenditures between 2005/06 to 2009/10. However, the share of government funding is expected to drop to 54% in 2010/11 from 64% in 2009/10 while the share of foreign funding will increase from 36% to 46% in the same period. This raises the issue of the sustainability of key health interventions in the event development partners reduce or pull out their funding.

Table 14: Source of funds for the public health sector (TZS billion)

| Sources | 2005/06 | 2006/07 | 2007/08 | 2008/09 | 2009/10 | 2010/11 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Actual Exp | Approved estimates | Actual Exp | Approved estimates | Actual Exp | Approved estimates | Actual Exp | Approved estimates | Actual Exp | Estimates |
| Government Funds | 296.82 | 370.99 | 348.89 | 413.26 | 378.11 | 459.50 | 461.50 | 548.66 | 578.68 | 643.01 |
| Foreign | 129.56 | 148.88 | 164.72 | 202.49 | 192.96 | 304.10 | 239.57 | 376.44 | 328.85 | 54971 |
| Basket | 68.30 | 99.91 | 103.20 | 80.96 | 80.96 | 99.73 | 85.40 | 121.64 | 128.80 | 161.80 |
| Non Basket | 61.26 | 48.97 | 61.51 | 121.53 | 112.00 | 204.37 | 154.17 | 254.80 | 200.05 | 387.91 |
| Off-Budget | 3.36 | - | 2.96 | - | 5.70 | - | 5.86 | - | 10.78 | - |
| Total | 429.74 | 519.87 | 516.57 | 615.75 | 576.77 | 763.59 | 706.93 | 925.10 | 918.31 | 1,192.72 |

## Budget Performance in the Health Sector

### Performance of the total Budget for the Health Sector

Performance of the Health Sector budget in 2008/09 was 95.53% down by 3.3% since 2006/07. The trend has nevertheless increased compared to the previous year when it was about 93%.

### Performance of the Recurrent Vs Development Budget

Overall, the budget performance has improved with all the resources allocated to the recurrent budget expended. In relation to the development vote, the expenditures are still low at 88% in 2009/10, and hence the need to identify the barriers hindering full absorption of resources which may include lack of release of funds and delay in procurement processes. Performance of the development budget has declined from almost hundred percent in 2006/07 to 88 %; implying that about 12% of the approved development budget end up not being spent in the sector.

Table 15: Budget performance – recurrent vs development

|  | 2006/07 | 2007/08 | 2008/09 | 2009/10 |
| --- | --- | --- | --- | --- |
| Total recurrent | 99% | 91% | 107% | 107% |
| Total development | 100% | 95% | 82% | 88% |
| Total (recurrent plus Development) | 99% | 93% | 92% | 98% |

### Budget Performance: Government versus Foreign Funds

The overall execution of the budget has improved, especially for the Government funds. However, absorption of foreign funds, especially non-basket funds, has declined from 126% in 2006/07 to 79% in 2009/10. Typical reasons for the low performance of the development budget have always been the cumbersome procurement procedures and non-release of the funds.

Table 16: Budget performance: Government vs foreign funds

|  | 2006/07 | 2007/08 | 2008/09 | 2009/10 |
| --- | --- | --- | --- | --- |
| Government Funds | 94% | 91% | 100% | 105% |
| Foreign | 111% | 95% | 87% | 87% |
| Basket | 103% | 100% | 87% | 106% |
| Non Basket | 126% | 92% | 87% | 79% |

### Budget Performance: MoHSW Departments

For consistency, the performance of activities by different departments is categorized in four levels as follows:

Level 1: 	Departments with funds utilization rate above 80% are considered to have fully implemented the activities as stipulated in the MTEF (excellent performance).

Level 2: 	Departments with funds utilization rate between 61%-80% are considered to have partially implemented the activities as stipulated in the MTEF (very good performance).

Level 3: 	Departments with funds utilization rate between 41%-60% are considered to have partially implemented the activities as stipulated in the MTEF (average performance).

Level 4: 	Departments with funds utilization rate between 0%-40% are considered poor Performers.

Except for the internal audit department which can be considered to have partially implemented the activities as stipulated in the MTEF (average performance), all other departments showed excellent and very good performance. The low performance of the internal audit department is attributed to non-release of the funds.

Table 17: MOHSW budget performance by departments, FY2009/10

| Department | Approved Estimates | Actual Expenditure | % Expenditure |
| --- | --- | --- | --- |
| Administration & Personnel | 3,872,092,721 | 3,669,771,318 | 95% |
| Finance & Accounts | 1,192.187,536 | 1,150,476,735 | 97% |
| Policy & Planning | 1,548.369,500 | 1,252,793,857 | 81% |
| Internal Audit | 290,541,500 | 159,057,756 | 55% |
| Information, education, & communication | 322,776,000 | 310,381,943 | 96% |
| Procurement unit | 425,377,503 | 389,724,189 | 92% |
| Legal unit | 198,596,340 | 186,211,738 | 94% |
| Hospital Services | 160,944,439,711 | 158,558,671,684 | 99% |
| Chief Medical Officer | 5,33,979,900 | 4,788,662,965 | 90% |
| Preventive Services | 34,874,454,808 | 29,766,282,941 | 85% |
| Social Welfare | 4,294,145,300 | 4,077,977,042 | 95% |
| Human Resource Development | 16,487,626,407 | 17,292,243,236 | 105% |
| Total Recurrent | 229,784,587,315 | 221,602,255,404 | 96% |

## Expenditures by Key Intervention Areas

The MoHSW spent 64% or TZS 245 billion in 2009/10 on key health sector priority areas, namely Malaria, TB, HIV &AIDS, Reproductive Health and Child Health and Pharmaceuticals. The largest expenditures of program funding were related to HIV & AIDS and Malaria at 42% and 14% respectively, as shown in Table 16 below.  Pharmaceuticals utilized 18% of all program funding. Of the funds spent on Reproductive and Child Health, 51% went to support family planning services.  It is important to note that the 11% expenditure indicated for reproductive and child health is underestimated. This is because most of the services are integrated and one can’t discern all the expenditures that go to reproductive and child health. In fact what this figure is reflecting is mostly preventive and not curative services. These expenditures are in line with priority areas identified in the HSSP III. It is important to note the MoHSW transfers funds to institutions/parastatals and this accounted for 21% of the total MoHSW expenditure in 2009/10.

Table 18: MOHSW expenditures by key intervention area, 2009/10

| Program | Recurrent Actual Expenditures | Development Actual Expenditures | Total | % of Total |
| --- | --- | --- | --- | --- |
| Malaria | 1,027,449,458 | 34,201,807,500 | 35,229,256,958 | 14% |
| TB/Leprosy | 617,900,000 | 34,191,421,256 | 34,809,321,256 | 14% |
| HIV & AIDS | 4,940,913,771 | 97,505,168,690 | 102,446,082,461 | 42% |
| Reproductive and child health | 6,907,297,608 | 21,156,873,072 | 28,064,170,680 | 11% |
| Family Planning |  | 14,372,476,195 | 14,372,476,195 | - |
| Vaccines | 3,243,674,582 | 3,126,000,000 | 6,369,674,582 | - |
| Others | 3,663,623,026 | 3,658,396,877 | 7,322,019,903 | - |
| Pharmaceuticals | 24,959,099,828 | 19,477,855,032 | 44,436,954,860 | 18% |
| Total | 38,452,660,665 | 206,533,125,550 | 244,985,786,215 | 100% |

Note: Family planning, vaccines and others are sub-sets of reproductive and child health.

### Health Sector Spending by MKUKUTA Objectives

Table 19 below presents figures on spending by MKUKUTA objectives. Except for expenditures by Internal Audit and Policy and Planning departments (54% and 78% respectively), all other departments spent over 80% of allocated funds.

Table 19: MKUKUTA-related expenditures, 2009/10

| Sub Vote | Department | MKUKUTA Related Budget (Million TZS) | MKUKUTA Cumulative Exp (Million TZS) | Exp as a % of budget |
| --- | --- | --- | --- | --- |
| 1001 | Administration & Personnel | 2,992,120,021 | 2,823,308,157 | 94% |
| 1002 | Finance & Accounts | 816,501,736 | 777,340,030 | 95% |
| 1003 | Policy & Planning | 1,305,530,500 | 1,014,005,078 | 78% |
| 1004 | Internal Audit | 290,541,500 | 158,057,757 | 54% |
| 1005 | Information, Education, & Communication | 322,776,000 | 310,381,943 | 96% |
| 1006 | Procurement Unit | 425,377,503 | 389,724,189 | 92% |
| 1007 | Legal Unit | 198,596,430 | 186,211,738 | 94% |
| 2001 | Hospital Services | 148,973,573,353 | 146,644,877,619 | 98% |
| 2003 | Chief Medical Officer | 5,333,979,900 | 4,788,662,965 | 90% |
| 3001 | Preventive Services | 32,936,606,008 | 27,652,578,678 | 84% |
| 4002 | Social Welfare | 2,042,834,700 | 1,900,430,087 | 93% |
| 5001 | Human Resource Development | 10,654,982,107 | 9,706,000,121 | 91% |
| Total recurrent |  | 195,638,437,651 | 196,351,578,362 | 100% |

### Health Expenditures among Layers of Government

Health expenditures continue to be concentrated at the central level (approximately 60%) mainly to support personnel emoluments and procurement of pharmaceuticals. The share of health resources spent at LGAs has been increasing from 24% in 2005/6 to 38% in 2009/10, which is in line with the decentralization framework. It was noted that in 2009/10, about 2% of the funds at central level was used for procurement of pharmaceuticals which are used at the LGA level.

Table 20: Health Expenditures among Layers of Government

|  | 2005/ 06 | 2006/07 | 2007/08 | 2008/09 | 2009/10 | 2010/11 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Actual | App-roved | Actual | App-roved | Actual | App-roved | Actual | App-roved | Actual | Estimates |
| Central | 72% | 66% | 62% | 60% | 59% | 61% | 58% | 54% | 55% | 60% |
| Regions | 4% | 5% | 5% | 7% | 7% | 7% | 8% | 6% | 7% | 6% |
| LGAs | 24% | 29% | 33% | 33% | 35% | 32% | 34% | 39% | 38% | 33% |
| Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |

### Health Sector Expenditure by the Categories of Spending Units

Analysis of expenditures in the health sector at the different levels is shown in Table 21 below. Usually, a significant proportion of the expenditure by the MoHSW ultimately goes down to the local level in the form of drugs and other essential supplies for health-service outlets. Also, the health resources managed by the PMO-RALG eventually go down to LGAs.

Table 21: Health sector expenditure by the categories of spending units

|  | 2005/06 | 2006/07 | 2007/08 | 2008/09 | 2009/10 | 2010/ 11 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Actual Exp | Approved Estimates | Actual Exp | App-roved Est-imates | Actual Exp | Approved Estimates | Actual Exp | App-roved Esti-mates | Actual Exp | Estimates |
| RECURRENT |
| NHIF | 20,457 | 24,050 | 23,950 | 27,971 | 26,719 | 30,177 | 34,325 | 41,283 | 39,782 | 63,700 |
| Ministry of Health |
| Govern-ment funds | 180,306 | 195,981 | 178,822 | 192,875 | 168,379 | 196,378 | 207,521 | 218,393 | 221,575 | 229,979 |
| Donor basket fund |  | 20,389 | 31,482 |  |  |  |  |  |  |  |
| Regional Administration |
| Government funds | 11,893 | 19115 | 19,052 | 28,761 | 26,024 | 30,927 | 32,218 | 37,447 | 36,214 | 42,933 |
| Local Government Authorities |
| Government funds | 75,314 | 114,779 | 115,392 | 145,286 | 139,168 | 144,902 | 154,494 | 201,488 | 235,171 | 242,000 |
| Donor basket fund | 20,075 | 23,331 | 23,094 |  |  |  |  |  |  |  |
| Total recurrent | 308,045 | 397,644 | 391,792 | 394,894 | 360,290 | 402,384 | 428,558 | 498,611 | 532,742 | 578,612 |
| DEVELOPMENT |
| Ministry of Health |
| Government funds | 5,000 | 7,123 | 7,010 | 5,481 | 4,940 | 13,029 | 11,778 | 13,029 | 9,339 | 9,874 |
| Donor basket fund | 28,486 | 34,766 | 25,534 | 36,595 | 36,595 | 49,302 | 36,247 | 50,331 | 64,606 | 58,315 |
| Foreign (non-basket) | 57,377 | 48,969 | 56,018 | 113,357 | 103,826 | 166,707 | 134,225 | 197,240 | 84,686 | 380,254 |
| PMO-RALG |
| Govern-ment funds | 100 | 70 | 70 | 57 | 57 | 23,057 | 56 | 56 | 56 |  |
| Donor basket fund | 19,738 | 21,424 |  | 450 | 450 | 650 | 1,626 | 687 | 687 | 1,895 |
| Foreign (non-basket) |  |  | 2,435 | 2,435 | 2,435 | 1,320 |  |  |  |  |
| Regional Administration |
| Government funds | 1,169 | 3852 | 2,435 | 7,848 | 7,848 | 10,012 | 10,097 | 13,862 | 13,545 | 16,225 |
| Donor basket fund |  |  |  |  |  | 2,100 | 1,905 | 4,200 | 4,257 | 5,051 |
| Foreign (non-basket) | 3,880 |  | 3,059 | 5,742 | 5,742 | 8,726 | 6,423 | 1,827 | 5,609 | 7,654 |
| Local Government Authorities |
| Government funds | 2,579 | 6,021 | 2,159 | 4,979 | 4,979 | 11,013 | 11,015 | 23,100 | 23,000 | 38,300 |
| Donor Basket Fund |  |  | 23,094 | 43,912 | 43,912 | 47,678 | 45,623 | 66,422 | 59,246 | 96,543 |
| Foreign (non-basket) |  |  |  |  |  | 27,615 | 13,520 | 55,734 | 9,754 |  |
| Total development | 118,329 | 122,226 | 121,814 | 220,854 | 210,782 | 361,209 | 272,515 | 426,488 | 374,785 | 614,111 |
| Total on budget | 426,374 | 519,871 | 513,606 | 615,748 | 571,073 | 763,593* | 701,073 | 925,099 | 907,527 | 1,192, 723 |
| OFF-BUDGET EXPENDITURE |
| HSF – Hospital | 2,698 |  | 2,964 |  | 5,696 |  | 5,858 |  | 9,767 |  |
| CHF – PHC | 666 |  |  |  |  |  |  |  | 1,017 |  |
| Total off budget | 3,363 |  | 2,964 |  | 5,696 |  | 5,858 | - | 10,784 |  |
| Grand total | 429,738 | 519,871 | 516,570 | 615,748 | 576,769 | 763,593 | 706,931 | 925,099 | 918,311 | 1,192, 723 |

## Pharmaceuticals

### Funding of pharmaceuticals and health commodities

Financing requirements are not well established.  Budget estimates for essential medicines and medical suppliesduring the MTEF process 2009 cited TZS 150 billion as the requirement, equivalent to about USD 2.50 per capita per year. However, budgets allocated from Government of Tanzania (GOT) and Health Basket Fund (HBF) for medicines provision through facility accounts at the Medical Stores Department (MSD) were only 33-40% of the estimated requirement. Complementary funding from local governments, and utilization of revenue from user fees and/or insurance funds can fill only a small part of this gap. Moreover, the increasing burden of non-communicable diseases may greatly increase this requirement of essential medicines for the most basic health interventions.

Budget estimates for allocation to MSD facility accounts do not include requirements of new high-cost pharmaceuticals and health commodities for disease control programmes (‘big ticket items’) that attract substantial external financing of over TZS 300 billion or about USD 5.00 per capita per year.  Big-ticket items include antiretroviral medicines, HIV test kits, new anti-malarials (artemisinin combination therapies; ACT), malaria rapid diagnostic tests, anti-TB medicines, new vaccines for immunization, and most recently maternal safe delivery packs.  Requirements of these big-ticket items are almost 100% funded, mainly through global health initiatives (GFATM, PEPFAR, PMI, GAVI). However, translating funds into a flow of commodities may be a lengthy and difficult process resulting in variation in annual spending and disruptions in availability. Actual spending is not easily captured due to different planning cycles, procurement and reporting mechanisms among the funding partners. Moreover, some of the financing for HIV-AIDS may be off-budget and/or multi-sectoral.

#### Allocations for essential medicines and medical supplies

The pooled budget for essential medicines and medical supplies has grown by more than 30 billion in nominal terms, from 45.5 billion in FY 2007/08 to 78.6 billion in FY 2011/12. This reflects substantial increase in support through the Basket Fund but declining GOT budget, as shown in Figure 30. However, in real terms the USD per capita budgetactually decreased from USD 0.90 to 0.84 per capita over the five-year period, and peaked at USD 0.95 per capita in FY 2008/09, as seen in Table 22.

Figure 37: Five year trend in the budget for essential medicines

Source: MOHSW Pharmaceutical Services Unit, based on MTEF

Actual performance over four years is affected by incomplete disbursement of GOT funds, averaging 70% over four years, as shown in Figures 38 and 39, as well as irregular and unpredictable release of funds over the year. Disbursement in FY 2010/11 was TZS 48.3 billion in nominal terms, or USD 0.75 per capita at current prices. This is a fall from FY 2008/09 –a good year in terms of budget performance – when TZS 51.3 billion was disbursed, equivalent to USD 0.92 per capita at FY 2008/09 prices.

Table 22: Real per capita budget for essential medicines (five years)

| BUDGETED | 2007-08 | 2008-09 | 2009-10 | 2010-11 | 2011-12 |
| --- | --- | --- | --- | --- | --- |
| Nominal (TZS Bil) | 45.463 | 53.430 | 49.600 | 63.875 | 78.641 |
| Real (TZS Bil) | 45.463 | 52.060 | 45.145 | 49.789 | 61.300 |
| Deflator (2007-08 baseline) | 1 | 1.03 | 1.10 | 1.28 | 1.41 |
| 1 USD Exchange Rate (TZS) | 1,262 | 1,320 | 1,327 | 1,468 | 1,468 |
| Population (millions) | 40.1 | 41.3 | 42.6 | 43.8 | 45.1 |
| Real USD per capita (ref. 2007-08 baseline) | 0.90 | 0.95 | 0.80 | 0.77 | 0.84 |

Source: MOHSW Pharmaceutical Services Unit analysis based on NBOS parameters 2007-2011; and estimating 2011/12 deflation based on 10% increase in CPI and static exchange rate.

Figure 38: Execution of the essential medicines budget over four financial years

Source: MOHSW Pharmaceutical Services Unit, based on PSU tracking information, funds transfers in IFMS and MSD reports on funds received

Figure 39: Budget performance by source of funds over four financial years

Source: MOHSW Pharmaceutical Services Unit, based on PSU tracking information, funds transfers in IFMS and MSD reports on funds received

In FY 2010/11 actual allocation of funds amounted to TZS 48.9 billion (Table 23). The planned proportion of funding by level was 50% for dispensaries and health centres (PHC), 40% for hospitals and 10% for ‘other’. However, actual allocations by level were greater than planned for the hospitals and other category, and less than planned for PHC, as shown in Table 23 below.

Table 23: Allocation of the essential medicines funds by level, FY2010/11

| ALLOCATION BY LEVEL(2010-11) | ACTUAL TZS BIL | ACTUAL ALLOC % | PLAN ALLOC % |
| --- | --- | --- | --- |
| PHC - DISP & HC (TZS BIL) | 19.1 | 39% | 50% |
| HOSPITALS (TZS BIL) | 22.9 | 47% | 40% |
| OTHER (TZS BIL) | 6.8 | 14% | 10% |
| TOTAL | 48.9 | 100% | 100% |

Source: MOHSW Pharmaceutical Services Unit tracking information

### Availability of tracer items at public health facilities

The CCHP (and HSSP) indicator “percentage of health facilities with continuous availability (no stock-out) of tracer” has not been reliably reported in recent years. The list of tracer items has been updated and the revised indicator will be piloted alongside the new HMIS/MTUHA. Meanwhile, proxy survey data on “percentage of health facilities with availability of tracers on the day of the survey” is reported here. Note that the proxy indicator is likely to overestimate availability compared with the indicator for a monthly or quarterly reporting period.

Data on availability of nine tracer commodities on the day of survey were obtained from the survey of commodities in the quarterly PMI end use assessmentsconducted over 10 quarters from January 2009 up to June 2011. On average, tracer commodities were available on the day of survey at 74% of health facilities (9 tracers over 10 quarters, in 500 facilities). Items with low availability were dextrose infusion (average 64%) and artemetherlumefantrine 4X6 tabs (ALu;average 67%). Items with high availability were cotrimoxazole tablets (average 85%) and amoxycillin capsules (average 79%).

Table 24 Quarterly availability of tracer medicines (10 quarters, 2009 to 2011)

Percentage of health facilities that have tracer medicine on the day of the survey

There is no evidence of improvement in availability over time. In FY 2010/11 tracer commodities were available at 71% of health facilities on average compared with 75%in FY 2009/10. Variation in availability across 10 quarters was high for ALu 4X6 tabs (26-90%) and ORS sachets (41-95%). The quarterly average availability (n=8 tracers) ranged from 65% to 81%.  However, this variation could reflect regional differences in availability, rather than variation in availability over time, because of the nature of the sampling.

Table 25: Trend in availability of tracer medicines (2009 to 2011)

Percentage of health facilities that have tracer medicine on the day of the survey

| Year | 2009/10 | 2010/11 | 2009-2011 | 2009-2011 | 2009-2011 |
| --- | --- | --- | --- | --- | --- |
| Quarter | AVG 4Q | AVG 4Q | AVG 10Q | MIN 10Q | MAX 10Q |
| Number of HF sampled | 80 | 380 | 500 | 500 | 500 |
| TRACER MEDICINES: |  |  |  |  |  |
| ALU 1X6 TABS | 72 | 75 | 73 | 50 | 89 |
| ALU 4X6 TABS | 70 | 57 | 67 | 26 | 90 |
| AMOXYCILLIN CAPS | 81 | 77 | 79 | 60 | 95 |
| ORS SACHETS | 89 | 59 | 77 | 41 | 95 |
| INJ CONTRACEPTIVE | 74 | 70 | 73 | 50 | 89 |
| ALBENDAZOLE TABS | 70 | 74 | 73 | 47 | 88 |
| COTRIMOXAZOLE TABS | 91 | 83 | 85 | 69 | 100 |
| DEXTROSE 5% INFUSION | 55 | 75 | 64 | 46 | 85 |
| MALARIA RDT |  | 74 | 74 | 63 | 79 |
| (AVG) | 75 | 71 | 74 | 65 | 81 |
| (MIN) | 55 | 57 | 64 |  |  |
| (MAX) | 91 | 83 | 85 |  |  |

These surveys did not include the important tracer line on oxytocics.A smaller surveyfound oxytocin injection available in only 33% of facilities (n=12) in Mtwara Region and 50% in Lindi Region (n=18), and noted that dispensaries and HCs are routinely ordering ergometrine injection not oxytocin.  Ergometrine injection was reportedly available in only 22% of the Mtwara facilities.

# Chapter 7: Human Resource Status in the Health Sector

The health sector continues to face the crisis of staff shortage. Acute lack of medical personnel is a national issue threatening operations to serve millions of patients/clients in countrywide. Referring back in year 2006 the statistics shows that a total of 82,277 health workers of various cadres were required. The actual numbers of various cadres for health in 2006 were 29,063 implying that there was a deficit of about 53,214 (65%) health workers in the public health facilities.  In December 2010, there were 52,637 workers in the entire health sector. The rising number of health workers is shown in Table 26 below.

Table 26: Available health workers

| YEAR | NUMBER AVAILABLE |
| --- | --- |
| Jan – June, 2005 | 29,063 |
| 2005/2006 | 33,715 |
| 2006/2007 | 38,527 |
| 2007/2008 | 41,537 |
| 2008/2009 | 44,547 |
| 2009/2010 | 48,637 |
| Dec 2010 | 52,637 |

Status of Health Workers in the national, referral and specialized hospitals by June 2010 is as shown in Table 27 below.

Table 27: Staff in national, referral and specialised hospitals

| HOSPITAL | NUMBER AVAILABLE |
| --- | --- |
| Muhimbili National Hospital | 3,100 |
| Muhimbili Orthopaedic Institute | 500 |
| KCMC | 1,350 |
| Bugando Hospital | 1,693 |
| Ocean Road Cancer Institute | 236 |
| Kibong’oto Hospital | 215 |
| Mirembe Hospital | 269 |
| Mbeya Referral Hospital | 650 |
| TOTAL | 8,013 |

In order to avert the threat posed by the crisis, concerted efforts by the Government and various stakeholders in the health sector are geared towards producing more human resources. In 2010/11 the Government enrolled a total of 5,926 students in the certificates, diploma and undergraduate degree programs. The same programs enrolled a total of 4,825 students in 2009/10. The increase in enrolment was 1,101 which surpass the target of increasing 850 students annually. The overall enrollment is shown in Table 28 below.

Table 28: Enrollment into training schools

| Year | Certificate | Diploma | Degree | Total |
| --- | --- | --- | --- | --- |
| 2009/10 | 2,344 | 1,373 | 1,108 | 4,825 |
| 2010/11 | 2,740 | 1,866 | 1,320 | 5,926 |

HSSP III has six indicators monitoring progress in relation to human resource availability:

- Medical officers and Assistant Medical Officers per 10,000 population (by region)

- Nurse-midwives per 10,000 population (by region)

- Pharmacists and pharmacy technicians per 10,000 population

- Health officers per 10,000 population

- Laboratory staff per 10,000 population

- No of training institutions with full accreditation from the National Council for Technical Education (NACTE).

Over the past few years, MOHSW has being developing a reliable system for capturing human resource for health information of all cadres, to show the human resource information status for the health sector.  This is a computerized Human Resource for Health Information System (HRHIS) that captures information on human resource for health comprehensively.  By November 2011 the computerized system had fully been rolled out throughout the country.

However, at the time of drafting, only five regions have accomplished the data entry exercise for year 2010.  These are Dar es Salaam, Kilimanjaro, Morogoro, Tanga and Pwani.  Also data from Muhimbili National Hospital has fully been entered in the computer.  The data for year 2010 from the mentioned regions and Muhimbili national hospital extracted from HRHIS is shown in Table 29 below.  It is expected that more complete data will be available from this source for the next Performance Profile Report.

Table 29: HR position in selected locations, 2010

| Cadre | Dar es Salaam | Kilimanjaro | Morogoro | Tanga | Pwani | Muhimbili National Hospital |
| --- | --- | --- | --- | --- | --- | --- |
| Assistant Biomedical Engineering Technician | 9 | 5 | 15 | 17 |  | 53 |
| Assistant Dental Surgeon Officer | 9 | 4 | 5 | 3 | 15 | 39 |
| Assistant Environmental Health Officer | 25 | 4 | 22 | 22 |  | 99 |
| Assistant Medical Officer | 74 | 32 | 66 | 57 | 60 | 416 |
| Assistant Nursing Officer | 57 | 12 | 26 | 86 | 53 | 333 |
| Clinical Assistant | 11 | 13 | 16 | 43 | 3 |  |
| Clinical Officer | 223 | 121 | 203 | 267 | 354 | 1,372 |
| Consultant Doctor | 12 | 1 | 4 |  | 4 | 24 |
| Consultant Environmental Officer | 1 |  |  |  |  | 1 |
| Dental Assistant | 3 | 2 | 4 | 5 | 7 | 22 |
| Dental Specialist | 1 |  | 2 |  |  | 5 |
| Dental Surgeon | 3 | 5 | 1 | 3 | 3 | 21 |
| Environmental Health Officer | 68 | 20 | 37 | 46 |  | 178 |
| Health Laboratory Scientist | 8 | 2 | 3 | 8 |  | 64 |
| Health Officer | 31 |  |  | 1 | 68 | 98 |
| Health Secretary | 4 | 5 | 8 | 10 | 8 | 46 |
| Medical Attendant | 117 | 56 | 138 | 336 | 471 | 2,684 |
| Medical Consultant |  |  |  |  |  | 21 |
| Medical Doctor | 22 | 10 | 15 | 14 | 41 | 135 |
| Medical Officer | 12 | 1 | 8 | 6 |  | 219 |
| Medical Record Officer | 2 |  | 16 | 8 |  | 32 |
| Medical Record Technician | 3 | 5 | 1 | 2 |  | 12 |
| Medical Specialist |  |  |  |  |  | 137 |
| Nurse | 410 | 320 | 427 | 265 | 262 | 2,458 |
| Nursing Midwife | 66 | 119 | 79 | 160 |  | 1,026 |
| Nursing Officer | 262 | 134 | 110 | 55 | 137 | 1,573 |
| Occupational Therapist | 2 | 1 | 1 |  |  | 17 |
| Pharmacist | 18 | 5 | 5 | 12 | 14 | 88 |
| Technician | 29 | 10 | 17 | 18 | 43 | 175 |
| Technologist |  |  | 2 | 16 |  | 80 |

Given the ongoing population of the HRHIS, data for calculation of the Human Resource indicators in the HSSP III are drawn from the latest version of the MOHSW Statistical Abstract.  Data are for 2010 and include councils and regional hospitals only, ie excluding higher level referral institutions and training institutions, which means that the actual number of staff will be under-stated in some specific regions.  Where comparison is given with 2009, data are taken from the Statistical Abstract of that year.  Some queries re completeness and accuracy remain, but these are the most complete data available at present.  As already noted, it is hoped that, for the next report, data will be provided by the HRHIS.

Medical Officers and Assistant Medical Officers per 10,000 population

Figure 40 below shows the regional values for this indicator, together with the national average.  The definition of Medical Officer used in this indicator includes Medical Officers and specialist doctors.

Figure 40:  Medical Officers and Assistant Medical Officers per 10,000 population, by region, 2010

The graph shows that the value of this indicator for Tanzania as a whole was 0.48, implying that in 2010 there was approximately one doctor or Assistant Medical Officer for every 21,000 inhabitants.  This is substantially lower than the 2008 baseline of 0.70 (1 per 14,200), which requires further investigation to determine whether it is due to data differences or an actual reduction in the ratio in the face of population growth. The regional values range from a high of 1.01 per 10,000 population in Pwani Region (one doctor/AMO per to a low of 9,950 persons in the region) to 0.22 per 10,000 in Tabora Region, ie less than one doctor or AMO for every 45,000 people in the latter region.

Review of the same data excluding the AMOs shows that Arusha Region has the highest ratio of doctors to population, at 0.39 per 10,000 (ie one doctor per 25,300), while Rukwa has the lowest at 0.05 per 10,000 (one doctor per almost 215,000).  The national average in 2010 was 0.14 per 10,000 (ie one doctor per 72,000 population), which is just less than a third of the HSSP III baseline for 2008 of 0.40, indicating a dramatic fall in the value over the past five years.  Again, further investigation is needed to determine to what extent this is a measurement problem.

The comparator indicator values for 2009 were 0.41 for MOs and AMOs together (ie 1 per 24,500 population), and 0.13 for MOs alone (ie 1 per 76,000), implying that some progress has been made over the last year.

Nurses and midwives per 10,000 population

Figure 41 below shows the national and regional values of the indicator of nursing staff availability.  Data are again taken from the latest draft Statistical Abstract, and combine figures for Trained and Enrolled Nurses.

Figure 41: Nurses and midwives per 10,000 population, by region, 2010

The graph shows that the national mean was 3.38 nurses and/or midwives per 10,000 population (equivalent to 1 nurse per 2,960 population), which is substantially higher than the 2008 baseline of 2.6.  As with the MOs and AMOs, there is significant regional variation, with Iringa having more than twice, and Kigoma slightly more than half of, the national average.

The comparator value of the indicator for 2009 was 2.65 per 10,000, or 1 nurse per 3,780 people, which implies that there has been a fifteen percent increase over the past year.

Pharmacy staff per 10,000

The indicator for regional availability of pharmacy staff includes both pharmacists and pharmacy technicians, but not pharmaceutical assistants.  Figure 42 shows that the national average was 0.08 pharmacy staff per 10,000 population, or one for every 127,000 people.  This is almost half of the baseline value of 0.15 reported for 2005.

Figure 42:  Pharmacy staff per 10,000 population, by region, 2010

The graph also shows that there was substantial variation in the indicator value by region.  Arusha Region had just over twice the national average number of pharmacy staff per 10,000 inhabitants, while Tanga region had the lowest availability at 0.03 per 10,000 population, ie less than half the national mean.

The comparison with the previous year shows that the availability of pharmacy staff has remained static in relation to the population at 0.08 per 10,000.

Health officers per 10,000 population

The number of health officers per 10,000 population is shown in Figure 43 below, with the national average at 0.28, representing one health officer for almost 36,000 people. This implies a slight increase from the 2005 baseline of 0.23 per 10,000 population.

Figure 43: Health officers per 10,000 population, by region, 2010

The graph shows that ten of the 21 regions are quite close to the mean, but that there are outliers on each end, with Pwani Region having the highest relative availability, at 0.48 (one per 25,000 people), while Manyara has less than a quarter of the mean value, at 0.06 per 10,000 population (one per 158,000).   The value for 2009 was 0.29 per 10,000 indicating a slight drop in availability of this cadre.

Laboratory staff per 10,000 population

The definition of laboratory staff includes both medical and chemical laboratory assistants, with the former by far the most numerous.  Figure 44 below shows the picture in 2010.

Figure 44:  Laboratory staff per 10,000 population, by region, 2010

The mean value for Tanzania is 0.14 per 10,000, ie one laboratory staff per 74,000 people.  This appears low when compared with the baseline figures of 0.27 in 2005, though it represents a slight increase from the value of 0.13 in 2009.

There is significant regional variation in the availability of the two cadres included here, with Arusha Region apparently having a far higher availability of laboratory staff than any other region, at 0.48 per 10,000 population (ie one per 21,000).  This is more than three times the mean, and 70% more than the next best staffed region (Pwani with 0.28 per 10,000)  Three regions, Tanga, Kigoma and Tabora, have 0.04 laboratory staff per 10,000 or less (ie one per 260,000 or more), implying that laboratory staff are in very short supply.

Data on the final HRH indicator comes from NACTE.  As of January 2012, the number of accredited institutions falling under the Health and Allied Sciences Board was as shown in Table 30 below.

Table 30: Accreditation status of Health and Allied Sciences training institutions

| Accreditation stage | Number of institutions | Description of stage |
| --- | --- | --- |
| Full | 26 | granted to institutions which have adequately met the above stipulated accreditation requirements |
| Provisional | 10 | granted to an institution which has not fulfilled all the stipulated requirements but which can be fulfilled within a specified time frame |
| Candidacy | 28 | Granted to institution once it attain full registration award upon fulfillment of some NACTE Academic Qualification Standards. The Council initially grants accreditation candidacy status to applicants after being convinced that they are undertaking the necessary steps to reach demonstrable compliance with the accreditation standards of the Council. |
| TOTAL | 64 |  |

Although this shows progress since the baseline figure of 1 by 2008, this shows that there is still a significant way to go before the 2015 target of 115 is reached.

# Chapter 8: Conclusion

This chapter summarises the issues and challenges which have been identified in the earlier sections or other reports pertaining to the financial year under consideration.

## Issues and challenges

- Timely compilation of data from routine HMIS and programs

- Limited capacity in data analysis and use at various levels

- A few indicators require surveys

- Review some targets to reflect the current situation

- Council failed to link problems, objectives, targets, interventions and activities

- Most of the stated objectives are not specific to the identified problems.

- Inadequate skills in  Computer  and PlanRep among the CHMTs and RHMTs

- Councils have failed to interpret the CCHP guideline and allocate resources to the priority areas.

- Problem of reporting data - Inconsistency, incomplete and incorrect data presentation in  different tables of the  CCHPs

- Newborns survival still a major challenge

- Large urban-rural differentials in parasite prevalence

## Areas of good performance

- Significant gains in child survival

- Contraceptive prevalence has surpassed the 2015 targets

- Great improvements in equitable coverage of ITNs between urban and rural communities

- Care seeking at health facilities is high

- TB  coverage indicators have been maintained at high levels

- Women receiving ARVs for MTCT has remained high

- Government budgeting, accounting and auditing processes are implemented in a transparent way

- Overall financial audits are improving

- Total Coverage for CHF and NHIF 2011 – 17.1%

Annexes

# Annex I: HSSP III Indicators up to 2010

| S/N | Indicator | Numer-ator | Denomi-nator | Baseline 2008 | 2010 status | Target by 2015 | Data Source | Type | Frequency |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Health Status |
| 1 | Neonatal mortality rate (per 1,000 live births) | Number of children who die within a first month of life | Number of live births in a year | 29 per 1000 live births (2007/08 (THIMS) | 26 per 1000 live births (TDHS 2009/10) | 19 per 1000 live births | TDHS, THMIS Population census | Impact | TDHS and THMIS intervals |
| 2 | Infant mortality rate (per 1,000 live births) | Number of children who die before reaching one year of age | Number of live births in a year | 58 per 1000 live births (2007/08 THMIS) | 51 per 1000 live births (TDHS 2009/10) | 50 per 1,000 live birth | TDHS, THMIS , Population Census | Impact | TDHS interval |
| 3 | Under-five mortality rate (per 1,000 live births) | Number of children who die before reaching five years of age | Number of live births within five years | 91 per 1000 live births (TDHS 2004/05) | 81 per 1000 live births (TDHS 2009/10) | 79 per 1000 live births in 2010 & 48 per 1000 in 2015 | TDHS, THMIS, Population census | Impact | TDHS interval |
| 4 | Proportion of under-fives severely underweight (weight for age) | Number of children under five years who were severely underweight | Number of children born in five years preceding the survey | 13% | 16.6% | 10% | TDHS | Impact | TDHS interval |
| 5 | Proportion of under-fives severely stunted (height for age) | Number of children under five years who were severely stunted | Number of children born in five years preceding the survey | <1% | 1.1% | 0.5% | TDHS | Impact | TDHS interval |
| 6 | Maternal mortality ratio (per 100,000 live births) | Number of maternal deaths | Number of 100,000 live births in a year | 578 Maternal deaths per 100,000 | 454 Maternal deaths per 100,000 | 265 Maternal deaths per 100,000 | TDHS | Impact | TDHS interval |
| 7 | Life expectancy at birth | Life Expectancy module | Life Expectancy module | Female 52 Male 51 (Census 2005) | Female 59 Male 57 (NBS projections based on Census 2005 results) | Female 62, Male 59, by 2025.4 | Census | Impact | Census Interval |
| 8 | Proportional of pregnant women who are under 20 years | Number of women under 20 who became pregnant in a year specified by the survey | Total number of women under 20 years as specified by the survey | 54% (TDHS 2004/05) | 39.2%1 | 39.2%1 | TDHS | Process | Annual/ TDHS interval |
| 9 | Total fertility rate of women 15-49 years | Total of fertility at a given point in time | Total number of women in the reproductive age group 15 – 49 years | 5.7% | 5.4% | Trend | TDHS | Impact | TDHS interval |
| 10 | HIV prevalence among pregnant women aged 15-24 | Number of pregnant women aged 15 – 24 years who were tested to be HIV positive | Total number of pregnant women in the age group 15 – 24 years during the survey period | 6.7% | 6.7% | 5% | THIMS | Impact | TDHS interval |
| 11 | HIV Prevalence Among 15-24 year old population male/female | Number of people aged 15 – 24 years who were tested to be HIV positive | Total population in the age group 15 – 24 years during the survey period | 6.1% (2004) | 6.1% (2004) | 5% | TDHS | Impact | TDHS interval |
| 12 | HIV prevalence among 15 - 49 years old population male/female | Number of people aged 15 – 49 years who were tested to be HIV positive | Total population in the age group 15 – 49 years who were tested during the survey period | Female 6.8% Male 4.7% All Sex 5.8% (THMIS 2007/08) | Female 6.8% Male 4.7% All Sex 5.8% (THMIS 2007/08) | Female 6.8% Male 4.7% All 5.8% (THMIS 2007/08) | THMIS | Impact | THMIS interval |
| 13 | Proportion of children orphaned by AIDS | Number of orphans due to AIDS | Total number of orphans | 10% (2005) | 10% (2005) | Trend | TDHS | Impact | TDHS interval |
| Service Delivery |
| General |
| 14 | Outpatient attendance per capita | Total number of OPD attendance in a year | Total population in a year | 0.68 | 0.74 | 0.80 | HMIS | Output | Annual |
| Vaccinations13 |
| 15 | V1 Proportion of children under one vaccinated against measles | Total number of children under one year vaccinated against measles | Total number of children under one year in a year | 92% | 84.4% | 85% | HMIS | Outcome | Annual TDHS interval |
| 16 | V2 Proportion of children under one vaccinated 3 times against DPT –Hb3 | Total number of children under one year vaccinated 3 times against DPT - Hb | Total number of children under one year in a year | 91% (HMIS 2007) | 61.3% | 90% in 90% of the districts2 | HMIS | Outcome | Annual TDHS interval |
| 17 | V3 Proportion of children under 5 receiving vitamin A twice per year | Number of children under 5 years who received vitamin A twice | Total number of children under 5 years in a year | 95% | 60.3% | 80%2 | HMIS TDHS | Outcome | Annual TDHS interval |
| 18 | V4 Proportion of women receiving at least 2nd doses of TT vaccination | Number of pregnant women who has received at least 2 doses of TT vaccination during pregnancy | Total number of pregnant women | 85 % | 73.1% | 85 % | HMIS TDHS | Outcome | Annual TDHS interval |
| Reproductive Health |
| 19 | Proportion of pregnant women start ANC before 16 weeks of gestation age | Number of pregnant women who start ANC before 16 weeks of gestation age | Total number pregnant women | 14% | 47% | Trend | HMIS | Process | Annual TDHS interval |
| 20 | Proportion of pregnant women attending ANC at least 4 times during pregnancy | Number of pregnant women attending ANC at least 4 times during pregnancy | Total number of pregnant women | 64% (2004/05) | 64% (2004/05) | 80% | HMIS TDHS | Outcome | Annual TDHS interval |
| 21 | Proportion of births attended by trained personnel in health facility | Number of deliveries conducted in health facilities | Projected number of births | 51% | 54% (HMIS) (50.6% Delivered by Health Professional, 50.2% delivered in a health facility) TDHS 2008/09 | 80% | HMIS | Outcome | Annual TDHS interval |
| 22 | Contraceptive prevalence rate | Number of contraceptive active users | Number of women of child bearing age | 20% (2004/05) | 28% | 30% | HMIS | Outcome | Annual TDHS interval |
| 23 | Percentage of (1) health Centers and (2) Dispensaries that can provide EmOC as defined in EHP | Number of (1) health Centers and (2) Dispensaries that can provide EmOC as defined in EHP | Total number of (1) health Centers and (2) Dispensaries providing reproductive and child health services | 5% (2004/05) Total average of (1)+(2) | 5% (2004/05) Total average of (1)+(2) | 40% (1) 40% (2) | Survey | Input | Survey |
| 24 | Maternal Case Fatality Rate in health facilities | Number deaths due to maternal complications | Number of women admitted due to maternal complications |  | 1909 deaths |  | HMIS | Output | Annual |
| HIV/AIDS |
| 25 | Percentage of HIV positive women receiving ARVs to prevent MTCT | Number of HIV positive women receiving ARVs for PMTCT | Number of HIV positive women | 34% (2007) | 50.9% | 80% | NACP | Output | Annual |
| 26 | Number of persons with advanced HIV infection receiving ARV combination treatment (disaggregated under 15 and 15 and above and sex) | Number of persons with advanced HIV infection receiving ARV combination treatment (disaggregated under 15 and 15and above and sex) | Projected number of persons with advanced HIV infection | (By end of 2007) 11,176 (<15) 124,470 (15+) | (By end of 2007) 11,176 (<15) 124,470 (15+) | t.b.d | NACP | Output | Annual |
| Malaria |
| 27 | Proportion of mothers who received two doses of preventive intermittent treatment for malaria during last pregnancy | Number of mothers receiving 2 doses of SP during pregnant within past 2 years | Number of mothers surveyed who delivered live births in past 2 years | 57% (2008) | 57% (2008) | 80% | MIS and other household surveys | Output | Annual |
| 28 | Proportion of vulnerable groups (pregnant women 15-49 yrs of age, children under 5) sleeping under an ITN the previous night | Number of children <5 or pregnant women 15-49 yrs sleeping under ITN night before survey | Number of children <5 or pregnant women 15-49 yrs who reside in surveyed households | <5 yrs: 26% PW: 27% (2008) | <5 yrs: 26% PW: 27% (2008) | 60% | MIS and other household surveys | Outcome | Annual |
| 29 | Proportion of laboratory confirmed malaria cases among all OPD visits (disaggregated under 5 and 5 and above) | Number of positive by microscopy or RDT | Number of OPD visits | Pending 2008 data under analysis |  | Pending | HMIS/Sentinel surveillance | Outcome | Annual |
| 30 | Prevalence of Malaria parasitaemia (under 5 years) | Number of children positive by microscopy | # children tested by microscopy | 18% (2008) |  | 5% | MIS and other household surveys | Impact | Biannual |
| Tuberculosis and Leprosy |
| 31 | TB Notification rate per 100,000 population | Number of tuberculosis cases diagnosed | Total population | 159/100,000 (new and retreatment) 61/100,000 (new sm+) | 153/100,000 (new and retreatment) 59/100,000 (new sm+) |  | NTLCP | Output | Annual |
| 32 | Percent of TB Cases Treatment success | Number of tuberculosis cases diagnosed | Number of patients who successfully completed treatment | 84.7% (2006) | 88.3% | 82% | NTLCP | Output | Annual |
| 33 | Proportion of Leprosy cases diagnosed and successfully completed treatment | Number of Leprosy cases diagnosed and successfully treated | Number of notified leprosy cases | PB 97% MB 91.7% | PB 95.6%(2008) MB 98.6%(2009) | t.b.d | NTLCP | output | Annual |
| Infectious and non-communicable diseases |
| 34 | Incidence of cholera | Number of cholera cases in a year | Total population at risk | 3,284 (2005) | 10,161 | t.b.d | HMIS | Outcome | Annual |
| 35 | Proportion of treated cases of cholera who died | Total number of treated cases of cholera who died | Total number of treated cholera cases |  | 1.4% | t.b.d | HMIS | Output | Annual |
| 36 | Proportion of adult with high blood pressure | Number of adults (24-65 years) with BP>140/90 | Adults (24-65) population in survey area | 37% (2007) | To be obtained from NIMR | Reduced by 25% | Special survey | Impact | End survey |
| Health Systems |
| Financial |
| 37 | Proportion of the National budget spend on health | National budget spend on health per given year | Total National budget spend per given year | 10.2% (PER 2007/08) | 10.14% | 15% | PER |  |  |
| 38 | Total GoT and donor (budget and off-budget) allocation to health per capita | Total GoT and donor (budget and off-budget) allocation to health | Total population | Tsh. 13,193 | Tsh. 22,967 | Tsh. 52,800 (MKUKUTA) | PER 2007/08 | Input | Annual |
| 39 | Proportion of population enrolled in CHF | Number enrolled on CHF | Total population | 9% | Data Not Available | 30% | PER | Process | Annual |
| Human Resources |
| 40 | Medical Officers and Assistant Medical Officers per 10,000 population (by region) | Number of MOs and AMOs available | Total population | 0.4 MO’s per 10,000 0.7 MO’s and AMO’s per 10,000 | 0.24 MO’s per 10,000 Popn 0.42 AMO’s per 10,000 Popn | t.b.d | HMIS | Input | Annual |
| 41 | Nurse-Midwives per 10,000 population (by region) | Number of Nurse-Midwives available | Total population | 2.6 per10,000 | 1.46 NM’s per 10,000 Popn | t.b.d | HMIS | Input | Annual |
| 42 | Pharmacists and pharmacy-technicians per 10,000 population (by region) | Number of Pharmacists and Pharmacy technicians available | Total population | 0.15 per 10,000 | 0.04 Pharmacists per 10,000 Popn 0.06 Pharmacy Technicians per 10,000 Popn | t.b.d | HMIS | Input | Annual |
| 43 | Health Officers per 10,000 population (by region) | Number of Health Officers available | Total population | 0.23 per 10,000 (2005) | 0.35 HO’s per 10,000 Popn | t.b.d | HMIS | Input | Annual |
| 44 | Laboratory staff per 10,000 population (by region) | Number of Laboratory staff available | Total population | 0.27 per 10,000 (2005) | 0.16 Lab. Staff per 10,000 Popn | t.b.d | HMIS | Input | Annual |
| 45 | Number of training institutions with full NACTE accreditation | Number of training institutions with full NACTE accreditation | Total number of training institutions | 1 | 15 | 116 | Baseline and End Survey | Process | Twice in HSSP III |
| Logistics |
| 46 | Percentage of public health facilities without any stock outs of 5 tracer drugs and 1 vaccine and medical devices and supplies (representing laboratory, theatre, ward and clinic) | Number of public health facilities without any stock outs of 5 tracer drugs and 1 vaccine and supplies (representing laboratory, theatre, ward and clinic) | Total number of public health facilities |  |  |  | Survey | Input | Annual |

# Annex II: Performance of Health Status Indicators

| NO. | INDICATOR | Other Sources | TDHS (2004/ 05) | THMIS (2007/08) | TDHS (2009/ 10) | TARGET by 2015 |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Neonatal mortality rate (per 1,000 live births) | - | 32 | 29 | 26 | 19 |
| 2. | Infant mortality rate (per 1,000 live births) | - | 68 | 58 | 51 | - |
| 3. | Under-five mortality rate (per 1,000 live births) | - | 112 | 91 | 81 | 54 |
| 4. | Proportion of under-fives who are underweight | - | 22% | - | 3.8% | 14% |
| 5. | Proportion of under-fives who are stunted | - | 38% |  | 16.5% | 22% |
| 6. | Maternal mortality ratio (per 100,000 live births | - | 578 |  | 454 | 265 |
| 7. | Life expectancy at birth | 52 (F) 51 (M) (Census2001/ 2002) | - | - |  | 62 (F) 59(M) (by 2025) |
| 8. | Proportion of pregnant women who are under 20 yrs |  | 54% | - |  | - |
| 9. | Total fertility rate of women 15-49 years |  | 5.7 | - | 5.4 | 5.2 |
| 10. | HIV Prevalence among 15-24 year old pregnant women tested | 6.8% (NACP 05/06) | - | - |  | - |
| 11. | HIV Prevalence among 15-24 year old population male/female |  |  | 3.6% (F) 1.1% (M) |  | - |
| 12. | HIV prevalence among 15 - 49 years old population male/female |  |  | 6.8% (F) 4.7% (M) |  | - |

# Annex III: OPD Attendance per capita by region in 2010

| S/No | Region | Total Attendance | Population Projection | OPD Attendance Per Capita |
| --- | --- | --- | --- | --- |
| 1 | ARUSHA | 1,624,697 | 1,664,780 | 0.98 |
| 2 | KILIMANJARO | 1,506,308 | 1,635,870 | 0.92 |
| 3 | TANGA | 2,617,228 | 1,966,908 | 1.33 |
| 4 | DODOMA | 1,412,136 | 2,111,763 | 0.67 |
| 5 | MANYARA | 809,804 | 1,388,295 | 0.58 |
| 6 | SINGIDA | 1,034,595 | 1,367,480 | 0.76 |
| 7 | TABORA | 1,204,480 | 2,349,374 | 0.51 |
| 8 | SHINYANGA | 2,203,074 | 3,841,788 | 0.57 |
| 9 | KIGOMA | 1,397,341 | 1,814,158 | 0.77 |
| 10 | MTWARA | 700,143 | 1,323,569 | 0.53 |
| 11 | LINDI | 686,390 | 923,607 | 0.74 |
| 12 | DAR ES SALAAM | 4,319,616 | 3,118,132 | 1.39 |
| 13 | MOROGORO | 1,906,205 | 2,115,275 | 0.90 |
| 14 | PWANI | 1,264,852 | 1,062,574 | 1.19 |
| 15 | IRINGA | 1,262,096 | 1,737,382 | 0.73 |
| 16 | MBEYA | 2,614,567 | 2,662,157 | 0.98 |
| 17 | RUKWA | 1,191,678 | 1,503,183 | 0.79 |
| 18 | RUVUMA | 1,105,375 | 1,375,017 | 0.80 |
| 19 | MWANZA | 3,065,616 | 3,566,263 | 0.86 |
| 20 | KAGERA | 1,337,778 | 2,563,870 | 0.52 |
| 21 | MARA | 1,977,780 | 1,822,866 | 1.08 |
| NATIONAL SUMMARY | 35,241,759 | 41,914,311 | 0.84 |

Source: HMIS Routine Data 2010, Population data NBS 2006

# Footnotes

Ie to be SMART – specific, measurable, attainable, relevant and time-bound

Hereafter the term “medicines” is used to mean “medicines and medical supplies, including diagnostic and dental supplies”

Adjusted for inflation, exchange rate and population growth with reference year 2007/08.

Other allocations refers to those MOHSW accounts at MSD for national emergencies, special medicines/ medical supplies distributed free of charge, and special services such renal dialysis. In FY 2010/11 funds were also allocated for bridging supplies of ARVs and HIV test kits.

Tracer items are: Vaccine DPT-HepB-HiB; Artemether-Lumefantrine oral; Amoxycillin or Cotrimoxazole oral; Albendazole or Mebendazole oral; Oral Rehydraton Solution; Ergometrine or Oxytocin inj. or Misoprostol oral; Medroxyprogesterone injectable contraceptive; Dextrose 5% or Dextrose-Saline IV sol.; Syringe and needle disposable; Malaria Rapid Diagnostic Test or supplies for malaria microscopy; plus two optional items to be decided at local government level.

End-Use Quarterly Reports, Qtr 1 of 2009 through Qtr 2 of 2011. USAID Deliver for NMCP and PSU funded by President’s Malaria Initiative.

Quarters 1-9 sample was 20 health facilities per quarter from four districts, comprised of 12 dispensaries, four health centres and four Council hospitals, selected from 4 regions (one district per region). In Quarter 10 the sample was increased substantially to 320 health facilities from 16 districts in 8 regions. The type and proportion of facilities after 6 months will be in the same facility sample.

The HSSP and CCHP tracer indicator monitors availability of oxytocin OR ergometrine injection, OR misoprostol tablets as any of these medicines are therapeutic alternatives suitable for management of excessive bleeding after delivery.

Availability and Management of Medicines and Medical Supplies.Findings from an assessment in 87 health facilities in 4 regions in Tanzania.Tanzanian German Programme to Support Health (TGPSH). Published and distributed by GIZ September 2011. Data collected Nov-2010 to Aug-2011.

MOHSW (2011). Annual health statistical abstract and figures. HMIS 2011.  As at 27 March 2012.  (data taken from pp 41-48)

National Road Map Strategic Plan to Accelerate Reduction of Maternal, Newborn and Child Deaths in Tanzania 2008 – 2015.

Abuja Declaration 2005

# Text boxes

HEALTH SECTOR PERFORMANCE PROFILE

REPORT 2011

| Ileje DC | 813,096,600 |
| --- | --- |
| Rorya DC | 447,599,400 |
| Lindi MC | 334,188,150 |
| Mkinga DC | 307,316,559 |
| Mpanda TC | 306,687,112 |
| Siha DC | 108,410,993 |

Councils allocated less than TSh 1 billion

| Kinondoni MC | 19,073,920,735 |
| --- | --- |
| Temeke MC | 15,003,365,911 |
| Kahama DC | 14,308,073,691 |
| Ilala MC | 12,523,171,740 |
| Mvomero DC | 12,301,708,248 |
| Arusha MC | 10,686,087,640 |
| Mbozi DC | 10,245,270,409 |

Councils allocated more than TSh 10 billion